## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURBA KHAMARSIMULIA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15134 | Augmentation | Supplying and laying of distribution system including providing Functional Household Tap Connection (FHTC) for Augmentation of Purbakhamar Simulia Piped Water Supply Scheme under Ranaghat Sub-Division, under Nadia Division, PHE Dte.. | Assistant Engineer | Junior Engineer 1 | ORD/000417/2023-2024 | 5224/ND | 24/11/2023 | 14/09/2026 | B.M. ENGINEERING & CONSTRUCTION | 215.24 | 28.13 | 13.07 | 75
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURBA KHAMARSIMULIA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15134 | Augmentation | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2,Junior Engineer 3 | ORD/000524/2022-2023 | 1269/ND | 23/03/2023 | 11/05/2025 | JOY HIND TUBEWELL'S | 65.37 | 13.55 | 20.72 | 100
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURBA KHAMARSIMULIA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15134 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Purba Khamarsimulia PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 105.00 Cu.m/hr | Assistant Engineer | Junior Engineer 1 | ORD/000469/2023-2024 | 136/ND | 09/01/2024 | 08/04/2024 | M/S R.K.ENTERPRISE | 99.27 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PURBA KHAMARSIMULIA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15134 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Puba Khamarsimulia ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15134) | Assistant Engineer | Junior Engineer | ORD/001464/2024-2025 | 235/EMD | 06/02/2025 | 01/10/2025 | ANUPAMA ENGINEERING WORKS | 11.76 | 0 | 0 | 100
Total | [13 empty] | 391.64 | 41.67 | 10.64