## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMALPUR ZONE-II (PHASE-II) IN RANAGHAT - II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15136 | Augmentation | Renovation of Partly-Gravity & Partly-Pressure Type AIRP of Capacity 25 Cu. M./ Hr. and Construction of Back Wash Chamber for AIRP at Head Work Site at Kamalpur Zone-II Piped water Supply Scheme under Ranaghat Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000544/2022-2023 | 1457/ND | 31/03/2023 | 30/05/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 58.65 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAMALPUR ZONE-II (PHASE-II) IN RANAGHAT - II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15136 | Augmentation | Continuation for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department. Period from 01.07.2023 to 30.09.2023. | Assistant Engineer | Junior Engineer 2 | ORD/000103/2023-2024 | 725/KLYSD-I | 22/06/2023 | 22/09/2023 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 4.89 | 0 | 0 | 100
Total | [13 empty] | 63.54 | 0 | 0