## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15138 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Krishnagar-I Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000523/2022-2023 | 1268/ND | 23/03/2023 | 22/05/2023 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 0 | 0 | 45
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15138 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Joania PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 55.00 Cu.m/hr | Assistant Engineer | Junior Engineer 1 | ORD/000491/2023-2024 | 6008/ND | 14/12/2023 | 03/12/2025 | ASIT PRAMANIK | 64.95 | 0 | 0 | 80
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15138 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Banpur ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15280) | Assistant Engineer |  | ORD/001455/2024-2025 | 228/EMD | 06/02/2025 | 08/03/2025 | BINAPANI ENTERPRISE | 11.76 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15138 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Joania ground water based water supply scheme under Block_ Krishnanagar_I Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15138) | Assistant Engineer | Junior Engineer | ORD/001462/2024-2025 | 233/EMD | 06/02/2025 | 08/03/2025 | SHRESTHA | 11.76 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JOANIA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15138 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No.- I AND II under Joania WS Scheme, Block Krishnagar I, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-06) | Assistant Engineer | Junior Engineer | ORD/000889/2022-2023 | 157/EMDdt.06.01.2023 | 08/02/2023 | 03/02/2025 | MASSK ENGINEERING WORKS | 14.9 | 0 | 0 | 100
Total | [13 empty] | 151.2 | 0 | 0