## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANPUR (PHASE-II) IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15280 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANPUR W/S Scheme, Block- Krishnaganj, ARABPUR W/S Scheme, Block-Karimpur, BHIMPUR W/S Scheme, Block-Krishnagar AND MONIPOTA W/S Scheme, Block- Krishnagar-I, Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/001444/2023-2024 | 5127/EMD | 04/09/2023 | 01/07/2025 | C.M.S. ENGINEERING CONCERN. | 70.97 | 0 | 0 | 12
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANPUR (PHASE-II) IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15280 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Santipur & Krishnaganj Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000530/2022-2023 | 1273/ND | 23/03/2023 | 22/05/2023 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 13.69 | 28.62 | 95
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANPUR (PHASE-II) IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15280 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Banpur ground water based water supply scheme under Block_ Krishnaganj Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15280) | Assistant Engineer |  | ORD/001455/2024-2025 | 228/EMD | 06/02/2025 | 08/03/2025 | BINAPANI ENTERPRISE | 11.76 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANPUR (PHASE-II) IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15280 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Banpur PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte. Capacity 70.00 Cu.m/hr | Assistant Engineer | Junior Engineer 3 | ORD/000465/2023-2024 | 132/ND | 09/01/2024 | 04/01/2025 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 82.08 | 77.01 | 93.82 | 98
Total | [13 empty] | 212.64 | 90.69 | 42.65