## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR FATEPUR (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15281 | Augmentation | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2,Junior Engineer 3 | ORD/000524/2022-2023 | 1269/ND | 23/03/2023 | 11/05/2025 | JOY HIND TUBEWELL'S | 65.37 | 12.97 | 19.84 | 100
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR FATEPUR (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15281 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Fatepur PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 45.00 Cu.m/hr. | Assistant Engineer | Junior Engineer 3 | ORD/000583/2023-2024 | 839/ND | 06/02/2024 | 02/11/2025 | ZEOLITE FRESH INDIA | 58.36 | 0 | 0 | 60
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR FATEPUR (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15281 | Augmentation | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000252/2024-2025 | 6290/ND | 26/09/2024 | 10/11/2024 | IMAGIN | 19.44 | 0 | 0 | 100
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR FATEPUR (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15281 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Fatepur ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15281) | Assistant Engineer | Junior Engineer | ORD/001460/2024-2025 | 231/EMD | 06/02/2025 | 01/10/2025 | RAJ & ENTERPRISE | 11.76 | 0 | 0 | 100
Total | [13 empty] | 154.94 | 12.97 | 8.37