## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Krishnagar-I | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Survey , Design and preperation of DPR in connection with Sandha piped water supply scheme in Krishnanagar I Block under Krishnanagar Sub Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000055/2023-2024 | 680/KSD | 26/05/2023 | 10/06/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.51 | 2.45 | 97.72 | 100
2 | NADIA | Krishnagar-I | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Laying of Distribution System including specials & valves, Laying of proposed Rising Main, Providing FHTC including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, repair and renovation works of R.C.C. Elevaced Reservoir of 90 and 270 Cum capacity, repair and renovation works of Pump Houses and other allied works at Sandha (State Arm Force) within Krishnagar I block under Krishnagar Sub-Divn under Nadia Divn, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000089/2023-2024 | 3025/ND | 14/07/2023 | 14/07/2026 | CHANDAN ROY, 35, M. M. GHOSH STREET, P.O. -KRISHNAGAR, DIST. NADIA, PIN -741101. | 247.85 | 134.7 | 54.35 | 55
3 | NADIA | Krishnagar-I | Eastern Mechanical | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under SANDHA ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001986/2023-2024 | 6967/EMD | 15/12/2023 | 01/07/2025 | CINZANO | 27.44 | 0 | 0 | 90
4 | NADIA | Krishnagar-I | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Sinking of 2 nos. Tubewell 300mm. x 200mm. dia 200 mtr deep by direct rotary rig method at headwork and 2nd tube well site for Sandha (SAF) water supply scheme under Krishnagar Sub-division under Nadia Division, PHE Dte. (SM/15520) | Assistant Engineer | Junior Engineer 4 | ORD/000035/2023-2024 | 2103/ND | 15/05/2023 | 14/07/2023 | B.M. ENGINEERING & CONSTRUCTION | 32.45 | 26.36 | 81.25 | 100
5 | NADIA | Krishnagar-I | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Material Requisition To Resource Division |  |  | RTOR000167/2022-2023 | 89/ND | 05/01/2023 | 05/01/2023 | Resource Division | 14.87 | 0 | 0 | 0
6 | NADIA | Krishnagar-I | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 50 m3/hr at Sandha SAP Water Supply Scheme within Krishnagar-I Block under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000789/2023-2024 | 1900/ND | 15/03/2024 | 06/09/2025 | JOY HIND TUBEWELL'S | 184.49 | 0 | 0 | 0
7 | NADIA | Krishnagar-I | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Material Requisition To Resource Division |  |  | RTOR000159/2023-2024 | 274/ND | 11/01/2024 | 11/01/2024 | Resource Division | 12.03 | 0 | 0 | 0
8 | NADIA | Krishnagar-I | Eastern Mechanical | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | New Service Connection charge for PH.No. 1 under Sandhya, 9th Battalian |  |  | BILL/04194/2023-2024 | BP-268-23-24 | 09/01/2024 | 09/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.36 | 0 | 0 | 0
9 | NADIA | Krishnagar-I | Eastern Mechanical | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | New Service Connection charge for PH.No. 2 under Sandhya, 9th Battalian |  |  | BILL/04195/2023-2024 | BP-267-23-24 | 09/01/2024 | 09/01/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.07 | 0 | 0 | 0
10 | NADIA | Krishnagar-I | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000295/2025-2026 | 3784/ND | 12/08/2025 | 12/09/2025 | IMAGIN | 34.21 | 0 | 0 | 0
11 | NADIA | Krishnagar-I | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
12 | NADIA | Krishnagar-I | Nadia Division | SANDHA PIPED WATER SUPPLY SCHEME BLOCK- KRISHNANAGAR-I, DIST - NADIA | SM/15520 | New | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000109/2025-2026 | 2229/ND | 13/05/2025 | 27/06/2025 | IMAGIN | 19.44 | 3.89 | 20 | 100
Total | [13 empty] | 682.68 | 167.4 | 24.52