## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | sinking of 80mm dia. Shallow tubewell for requirement of drilling water for Fulia Township (Z-I) PWSS, District Nadia and other PWSS under CMSD-II (D), CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000073/2023-2024 | 103/CMSD-II(D) | 20/04/2023 | 05/05/2023 | UNIVERSAL ENTERPRISES | 0.88 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1883/ND | 26/04/2023 | 26/04/2023 | Resource Division | 33.17 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 0 | 0 | 40
4 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Fulia Township W/S Scheme (Z- I, T/W-III),Santipur Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000096/2023-2024 | 516/CDD | 01/06/2023 | 01/02/2025 | M/S S.K.GHOSH & CO. | 18.88 | 0 | 0 | 0
5 | NADIA |  | Central Drilling | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 250 Mtrs. Depth) by utilising departmental machineries for Fulia Township W/S Scheme (Z-I, T/W I & II). Santipur Block under Nadia District, Central Drilling Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000035/2023-2024 | 515/CDD | 01/06/2023 | 29/08/2024 | UNIVERSAL ENTERPRISES | 37.73 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Construction Of Pump House (5.4m X 3.6m) Including Sanitary Arrangemen At Hw Site At Fulia Zone-I Water Supply Scheme Under Ranaghat Sub-Division PHE Dte.) | Assistant Engineer | Junior Engineer 2 | ORD/000363/2023-2024 | 4698/ND | 11/10/2023 | 09/01/2024 | M/S BISWAS ENTERPRISE | 6.88 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 7561/ND | 27/12/2024 | 27/12/2024 | Resource Division | 23.37 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | New Power Connection charges for FULIA Water Supply Scheme Z -I , Pump House No- II |  |  | BILL/02297/2024-2025 | BP-185 | 13/12/2024 | 13/12/2024 | W.B.S.E.D.C.L (FULIA C.C.C) | 5.36 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | New Power Connection Charges for FULIA Water Supply Scheme Z - I , HEAD WORK SITE (PH-I) |  |  | BILL/02298/2024-2025 | BP-186 | 13/12/2024 | 13/12/2024 | W.B.S.E.D.C.L (FULIA C.C.C) | 14.29 | 0 | 0 | 0
10 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | New Power Connection Charges for FULIA Water Supply Scheme Z- I , Pump House No- III |  |  | BILL/02299/2024-2025 | BP-187 | 13/12/2024 | 13/12/2024 | W.B.S.E.D.C.L (FULIA C.C.C) | 5.21 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Providing functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete Construction Of 700 Cum Capacity 20 Mtr. Staging Height RCC Over Head Reservoir (Including Pile Foundation), Pipe Connection And Cost Of Pipes, Specials & Soil Investigation For Construction Of One No. 700 Cum OHR Of Staging Height 20 Mtr. for augmentation of Ground Water Based Water Supply Scheme For Fulia Township Zone-I to accommodate FHTC in Santipur block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000195/2023-2024 | 3450/ND | 09/08/2023 | 09/08/2025 | APURBA MONDAL, VILL+P.O. BADKULLA, DIST.NADIA, PIN-741121 W.B | 746.37 | 0 | 0 | 85
12 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Construction of 56.00 mtr long Boundary Wall (2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-I Pump House-III under Ranaghat Sub-Division, Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000796/2024-2025 | 87/RSD | 14/01/2025 | 30/03/2025 | ROMI TRADERS | 4.77 | 0 | 0 | 0
13 | NADIA |  | Eastern Mechanical | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, II and III , Zone-I under Fulia Town Ship (Zone-I) ground water based water supply scheme under Block_ Santipur Dist. - Nadia under EMD, PHE Dte. [SM-15522] | Assistant Engineer | Junior Engineer | ORD/000340/2024-2025 | 2155/EMD | 30/08/2024 | 11/09/2025 | KARTICK BAL | 42.39 | 0 | 0 | 70
14 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 135 cum/Hour capacity for Augmentation of Ground Based Water Supply Scheme at Fulia Township Zone-I to accommodate FHTC within Santipur block under Ranaghat Sub-division under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000707/2024-2025 | 137/ND | 08/01/2025 | 07/07/2025 | MONDAL ENTERPRISE | 245 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Construction of Pump House (3.6m x 3.0m) Including Sanitary Arrangement at Pump house No-2 site at Fulia Zone-I Water supply scheme under Ranaghat Sub ¿ Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000219/2024-2025 | 1184/RSD | 25/09/2024 | 09/12/2024 | ASHIM ENTERPRISE | 4.46 | 0 | 0 | 100
16 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Providing leave out functional household tap connection including supplying, laying, fitting, fixing of 15mm NB PVC (schedule 80)/20mm OD HDPE (PE100, PN16) pipe with all necessary specials, saddle piece etc. all complete for augmentation of Ground Water Based Water Supply Scheme for Fulia Township Zone-I to accommodate FHTC in Santipur block and allied works of Badkulla Zone II of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000018/2025-2026 | 1804/ND | 22/04/2025 | 19/10/2025 | APURBA MANDAL | 64.83 | 0 | 0 | 90
17 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Construction of 44 mtr long Boundary Wall(2.5m panel) having 200X200 mm R.C.C. Column footing (1.0X1.0 m) with 125mm thick brick panel wall and 200x300 mm tie beam at GL including M.S gate at Fulia Zone-I Pump House-II under Ranaghat Sub-Div, Nadia Division PHE. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000915/2024-2025 | 86/RSD | 14/01/2025 | 30/03/2025 | BRICK FARM | 4.05 | 0 | 0 | 0
18 | NADIA |  | Nadia Division | PROVIDING FHTC BY AUGMENTATION FOR FULIA TOWNSHIP (ZONE-I) PWSS, BLOCK: SANTIPUR, DISTRICT: NADIA | SM/15522 | Augmentation | Continuation for Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000296/2025-2026 | 3785/ND | 12/08/2025 | 11/10/2025 | IMAGIN | 96.97 | 0 | 0 | 0
Total | [13 empty] | 1451.56 | 0 | 0