## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15538 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000527/2022-2023 | 1270/ND | 23/03/2023 | 22/05/2023 | AUXILIARY TUBEWELL DRILLERS | 65.32 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15538 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under DAKSHINPARA (Zone-I & II) W/S Scheme, Block- Hanskhali , AND GOPINATHPUR W/S Scheme, Block- Tehatta-II, Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001008/2022-2023 | 496/EMDdt.24.01.2023 | 17/03/2023 | 01/01/2025 | GLACIER ENGINEERING CO. | 66.71 | 0 | 0 | 100
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15538 | Augmentation | Construction of Backwash chamber of AIRP at Head Work Site & Renovation of Gravity Type AIRP in Dakshinpara-II PWSS within Ranaghat Sub-Division under Nadia Division PHE Dte.Capacity 35.00 Cu.m/hr | Assistant Engineer | Junior Engineer 2 | ORD/000467/2023-2024 | 134/ND | 09/01/2024 | 03/04/2025 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 60.46 | 0 | 0 | 91
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHINPARA ZONE-II (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15538 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Dakshinpara Zone-II ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15538) | Assistant Engineer |  | ORD/001458/2024-2025 | 230/EMD | 06/02/2025 | 08/03/2025 | SK ENTERPRISE | 11.76 | 0 | 0 | 0
Total | [13 empty] | 204.25 | 0 | 0