## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15539 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augomentation in connection to Accommodate FHTC at Pump House No.-I/II under Gazna ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000014/2024-2025 | 1306/EMD | 09/05/2024 | 08/06/2024 | RAJ & ENTERPRISE | 7.67 | 7.66 | 99.77 | 100
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15539 | Augmentation | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000252/2024-2025 | 6290/ND | 26/09/2024 | 10/11/2024 | IMAGIN | 19.44 | 0 | 0 | 100
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15539 | Augmentation | New single phase service connection at Gazna (Part) water supply scheme at Hanskhali block, Dist.-Nadia |  |  | BILL/00332/2024-2025 | BP-21-24-25 | 21/05/2024 | 21/05/2024 | W.B.S.E.D.C.LTD (BAGULA C.C.C) | 0.26 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15539 | Augmentation | Replacemt of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Gazna PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. (Balance) A- Part. | Assistant Engineer | Junior Engineer 2 | ORD/000370/2023-2024 | 4802/ND | 17/10/2023 | 15/01/2024 | SANDIP BISWAS | 99.5 | 0 | 0 | 96
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15539 | Augmentation | Renovation of Semi-Gravity & Semi-Pressure Type AIRP at Gazna Water Supply Scheme of capacity 58.5 Cu.m/hr. | Assistant Engineer | Junior Engineer 2 | ORD/000553/2023-2024 | 783/ND | 05/02/2024 | 05/05/2024 | APURBA MANDAL | 44.96 | 17.72 | 39.41 | 84
6 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15539 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Replacement Tube Well in connection to Accommodate FHTC at Pump House No.-I under Gazna ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte.(Phase-II) (SM/15539) | Assistant Engineer |  | ORD/001461/2024-2025 | 232/EMD | 06/02/2025 | 08/03/2025 | MAA KALI ENTERPRISE | 11.76 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GAZNA (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15539 | Augmentation | Sinking of Rig Bored Tube well (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2,Junior Engineer 3 | ORD/000524/2022-2023 | 1269/ND | 23/03/2023 | 11/05/2025 | JOY HIND TUBEWELL'S | 65.37 | 12.87 | 19.69 | 100
Total | [13 empty] | 248.96 | 38.24 | 15.36