## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHISHNENGRA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15540 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accomodate FHTC under MAHISNENGRA (Zone-I) W/S Scheme, Block- Krishnagar-1 , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 16) |  |  | ORD/002775/2022-2023 | 416/EMDdt.20.01.23 | 17/02/2023 | 19/03/2023 | GOENKA ENTERPRISE | 14.03 | 0 | 0 | 90
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHISHNENGRA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15540 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Krishnagar-I Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000523/2022-2023 | 1268/ND | 23/03/2023 | 22/05/2023 | B.M. ENGINEERING & CONSTRUCTION | 47.83 | 0 | 0 | 45
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAHISHNENGRA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/15540 | Augmentation | Continuation work for Making & Fixation of Information Board (Swajal/Scheme) for various augmentation schemes with related to Jal Jeevan Mission ( JJM) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000252/2024-2025 | 6290/ND | 26/09/2024 | 10/11/2024 | IMAGIN | 19.44 | 0 | 0 | 100
Total | [13 empty] | 81.3 | 0 | 0