## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Nabadwip | Central Drilling | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Char Brahmanagar W/S Scheme (TW-III) , Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000135/2023-2024 | 1657/CDD | 17/10/2023 | 16/11/2023 | SNEHASISH GHOSH | 16.33 | 0 | 0 | 0
2 | NADIA | Nabadwip | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Material Requisition To Resource Division |  |  | RTOR000169/2022-2023 | 128/ND | 05/01/2023 | 05/01/2023 | Resource Division | 119.68 | 0 | 0 | 0
3 | NADIA | Nabadwip | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Installation of Har Ghar Jal (HGJ) Display Board at different Villages under various PWSS under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000419/2023-2024 | 5349/ND | 01/12/2023 | 30/01/2024 | IMAGIN | 96.97 | 1.4 | 1.44 | 40
4 | NADIA | Nabadwip | Eastern Mechanical | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation NEW Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III under Char Brahmanagar ground water based water supply scheme under Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. (SM/16182) | Assistant Engineer |  | ORD/000640/2024-2025 | 2677/EMD | 20/11/2024 | 20/12/2024 | HINDUSTAN ENGINEERING CORPORATION(E & M) | 36.01 | 0 | 0 | 0
5 | NADIA | Nabadwip | Central Drilling | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Char Brahmanagar W/S Scheme (TW-I) ,Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000241/2023-2024 | 1655/CDD | 17/10/2023 | 01/08/2024 | GENUINE | 16.88 | 3.43 | 20.33 | 100
6 | NADIA | Nabadwip | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Material Requisition To Resource Division |  |  | RTOR000151/2023-2024 | 262/ND | 11/01/2024 | 11/01/2024 | Resource Division | 25.02 | 0 | 0 | 0
7 | NADIA | Nabadwip | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 3315/ND | 11/06/2024 | 11/06/2024 | Resource Division | 20.41 | 0 | 0 | 0
8 | NADIA | Nabadwip | Eastern Mechanical | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Quotation for new service connection for Char Bramhanagar Ph-2, under Nabadwip block, District-Nadia |  |  | BILL/02313/2024-2025 | BP-203-24-25 | 17/12/2024 | 17/12/2024 | WBSEDCL SWARUPGANJ C.C.C. | 9.86 | 0 | 0 | 0
9 | NADIA | Nabadwip | Eastern Mechanical | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Quotation for new service connection for Char Bramhanagar Ph-1, under Nabadwip block, District-Nadia |  |  | BILL/02320/2024-2025 | BP-202-24-25 | 17/12/2024 | 17/12/2024 | WBSEDCL SWARUPGANJ C.C.C. | 12.62 | 0 | 0 | 0
10 | NADIA | Nabadwip | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 120 m3/hr at Char Brahmanagar Water Supply Scheme within Nabadwip Block under Krishnagar Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000119/2024-2025 | 4521/ND | 20/08/2024 | 11/02/2026 | MONDAL PRECISION PRIVATE LIMITED | 296.98 | 0 | 0 | 0
11 | NADIA | Nabadwip | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Construction Of Approach Road To The Headwork Site With Pilling Work, Land Development Of Head Worksite, Restoration Of Concrete Roads And Allied Works Of Char Brahmanagar Water Supply Scheme Under Krishnagar Subdivision Under Nadia Division PHED. | Assistant Engineer | Junior Engineer 4 | ORD/000267/2024-2025 | 6625/ND | 25/10/2024 | 24/03/2025 | H I ENTERPRISE | 74.95 | 0 | 0 | 50
12 | NADIA | Nabadwip | Nadia Division | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Additional Laying of UPVC Pipeline for providing leftout FHTC including supplying, laying, fitting, fixing with all necessary specials, saddle piece etc. all complete for Ground Based piped water supply scheme in Char Majhdia Char Brahmanagar to accommodate FHTC within Nabadwip block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000142/2025-2026 | 3072/ND | 01/07/2025 | 28/12/2025 | H I ENTERPRISE | 90.88 | 0 | 0 | 40
13 | NADIA | Nabadwip | Central Drilling | Char Brahmanagar Piped Water Supply Scheme.(JJM Revision) | SM/16182 | New | Providing drilling crew and other allied works for construction of Tube Well ( 300mm X200mm X 250 Mtrs. Depth) by utilising Departmental Machineries for Char Brahmanagar W/S Scheme (TW-II) ,Krishnagar-I Block under Nadia District, Central Drilling Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000242/2023-2024 | 1656/CDD | 17/10/2023 | 01/04/2025 | GENUINE | 16.88 | 0 | 0 | 100
Total | [13 empty] | 833.45 | 4.83 | 0.58