## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17195 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Tenipur Zone-I Piped Water Supply Scheme, Block: Karimpur-II Dist. Nadia Under EMD, PHE Dte. |  |  | ORD/001909/2023-2024 | 6733/EMD | 29/11/2023 | 29/12/2023 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.1 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17195 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site of Teinpur Zone-I [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000518/2022-2023 | 1217/ND | 21/03/2023 | 20/05/2023 | JOY HIND TUBEWELL'S | 14.38 | 0 | 0 | 85
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17195 | Augmentation | Renovation and modification of AIRP (Pressure Type) & Construction of Backwash chamber for AIRP at Head Work Site in Teinpur ZONE-I PWSS under Nadia Division PHE Dte. Capacity- 15.5 cum/hr. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000551/2023-2024 | 781/ND | 05/02/2024 | 05/05/2024 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 37.22 | 0 | 0 | 93
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17195 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under TEINPUR (ZONE-I ,II, III & IV) W/S Scheme, Block- Karimpur-II , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 06) |  |  | ORD/002611/2023-2024 | 500EMD | 24/01/2024 | 23/02/2024 | M/S DILIP MITRA | 64.62 | 0 | 0 | 85
5 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17195 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Teinpur Zone-IV PWSS within Karimpur-II Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000006/2024-2025 | 3260/ND | 10/06/2024 | 03/09/2025 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 82.42 | 0 | 0 | 80
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone I PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17195 | Augmentation | Laying of 160 mm dia HDPE pipe line, 75 mm & 125 mm UPVC Pipe line for Augmentation of Rising Main System for distribution pipeline with interconnection along with road restoration at village Dogachhi, Block Karimpur-II under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Nabadwip Block | ORD/000017/2025-2026 | 1803/ND | 22/04/2025 | 19/10/2025 | SUBHASH BOSE | 32.54 | 0 | 0 | 51
Total | [13 empty] | 273.29 | 0 | 0