## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17202 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. rejuvenation to Accommodate FHTC at Pump House No.- II under Fazilnagar W/S Scheme,, Block-Karimpur-II, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 09) |  |  | ORD/000517/2022-2023 | 6273/EMD | 18/11/2022 | 18/12/2022 | SRI KRISHNA NIRMAN | 5.85 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17202 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer etc. rejuvenation to Accomodate FHTC at Pump House No.- III under Fazilnagar W/S Scheme, Block-Karimpur-II, Dist. - Nadia. NIET No.- 18 of EEW/EMD of 2022-23 (Sl. No.- 10) |  |  | ORD/000518/2022-2023 | 6274/EMD | 18/11/2022 | 18/12/2022 | ASHOKE ADHIKARY | 8.74 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17202 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Fazilnagar (Phase-II) Piped Water Supply Scheme Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. |  |  | ORD/001759/2023-2024 | 6370/EMD | 17/10/2023 | 16/11/2023 | R.N.S. TRADING | 53.72 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17202 | Augmentation | Augmentation of FHTC (Part-B) of Fazilnagar Pipe Water Supply Scheme. |  |  | ORD/000160/2024-2025 | 4903/ND | 10/09/2024 | 09/11/2024 | PATHIK PABAN NANDI | 34.31 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17202 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accomodate FHTC at Pump House No.- I under Fazilnagar W/S Scheme, Block-Karimpur-II, Dist. - Nadia. NIET No.- 18 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer | ORD/000200/2022-2023 | 6189/EMDdt.14-11.2022 | 16/03/2023 | 15/04/2023 | GHOSE ENGINEERING SYNDICATE | 13.61 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17202 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site & 2nd Tube Well Site of Fazil Nagar [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000521/2022-2023 | 1248/ND | 22/03/2023 | 21/05/2023 | B.M. ENGINEERING & CONSTRUCTION | 29.32 | 0 | 0 | 70
7 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Fazilnagar PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17202 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 117 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Fazilnagar PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000029/2023-2024 | 1787/ND | 20/04/2023 | 22/09/2025 | B.M. ENGINEERING & CONSTRUCTION | 118.29 | 0 | 0 | 30
Total | [13 empty] | 263.84 | 0 | 0