## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Ber Ramchandrapur Zone II PWSS (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17203 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I & II Zone-II(Phase-II) under Ber Ramchandrapur ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. |  |  | ORD/001769/2023-2024 | 6393/EMD | 30/10/2023 | 29/11/2023 | SHIVAM ENTERPRISE | 16.27 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Ber Ramchandrapur Zone II PWSS (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17203 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000105/2023-2024 | 3787/ND | 24/08/2023 | 24/08/2023 | Resource Division | 2.94 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Ber Ramchandrapur Zone II PWSS (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17203 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site & 2nd Tube Well Site of Ber Ramchandrapur Zone-II [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000516/2022-2023 | 1193/ND | 21/03/2023 | 20/05/2023 | B.M. ENGINEERING & CONSTRUCTION | 28.7 | 18.62 | 64.9 | 70
Total | [13 empty] | 47.9 | 18.62 | 38.87