## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Uttar Tajpur PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17204 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at UTTAR TAJPUR (PHASE-II) Piped Water Supply Scheme, Block:KARIMPUR-II, Dist. Nadia Under EMD, PHE Dte. |  |  | ORD/001748/2023-2024 | 6359/EMD | 17/10/2023 | 16/11/2023 | SANKAR PRASAD DUTTA & CO | 41.45 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Uttar Tajpur PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17204 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Uttartajpur PWSS within Karimpur-I Block underTehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000478/2024-2025 | 7264/ND | 13/12/2024 | 27/01/2025 | GOUTAM DEY | 12.19 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Uttar Tajpur PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17204 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 45 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Uttar Tajpur PWSS under Nadia Division PHE Dte. | Assistant Engineer |  | ORD/000010/2023-2024 | 1806 / ND | 24/04/2023 | 23/07/2023 | APURBA MANDAL | 85.67 | 0 | 0 | 60
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Uttar Tajpur PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17204 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Uttartajpur PWSS under Karimpur-I Block under Tehatta Sub Division under Nadia Division-,P.H.E Dte. under Jal Jeevan Mission(JJM) . | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000745/2024-2025 | 423/ND | 27/01/2025 | 23/11/2025 | NISHITH BANERJEE | 26.22 | 0 | 0 | 60
Total | [13 empty] | 165.54 | 0 | 0