## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17205 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2023-2024 | 3788/ND | 24/08/2023 | 24/08/2023 | Resource Division | 3.21 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17205 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under MADHUGARI W/S Scheme, Block- Karimpur-1 , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 20) | Assistant Engineer | Junior Engineer | ORD/000910/2022-2023 | 420/EMDdt.20.01.2023 | 17/03/2023 | 16/04/2023 | KARUNAMOY ENGINEERING | 9.86 | 9.57 | 97.04 | 100
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17205 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site & 2nd Tube Well Site of Madhugari [Phase-III] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000517/2022-2023 | 1194/ND | 21/03/2023 | 20/05/2023 | B.M. ENGINEERING & CONSTRUCTION | 28.53 | 19.22 | 67.36 | 70
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MADHUGARI PWSS (PHASE-III) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17205 | Augmentation | Repairing Works (existing OHR, Pump House, Boundary wall etc.) of Madhugari Water Supply Scheme, Karimpur-I Block Under R.W.S. Nadia Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000030/2024-2025 | 3431/ND | 19/06/2024 | 14/06/2025 | M/S DURGA SECURITIES & SERVICES | 22.18 | 5.71 | 25.73 | 100
Total | [13 empty] | 63.78 | 34.49 | 54.09