## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone II PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17206 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-II(Phase-II) under Teinpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. |  |  | ORD/001770/2023-2024 | 6394/EMD | 30/10/2023 | 29/11/2023 | D.S. ENTERPRISE | 8.45 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone II PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17206 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site of Teinpur Zone-II [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000519/2022-2023 | 1218/ND | 21/03/2023 | 20/05/2023 | JOY HIND TUBEWELL'S | 14.37 | 9.64 | 67.05 | 85
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone II PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17206 | Augmentation | Laying of 160 mm dia HDPE pipe line, 75 mm & 125 mm UPVC Pipe line for Augmentation of Rising Main System for distribution pipeline with interconnection along with road restoration at village Dogachhi, Block Karimpur-II under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Nabadwip Block | ORD/000017/2025-2026 | 1803/ND | 22/04/2025 | 19/10/2025 | SUBHASH BOSE | 32.54 | 0 | 0 | 51
Total | [13 empty] | 55.37 | 9.64 | 17.4