## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Muktadaha zone I (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17207 | Augmentation | Renovation of AIRP (Pressure Type ) of capacity 33.75 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Muktadaha Zone I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000025/2023-2024 | 1783/ND | 20/04/2023 | 19/07/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 201.98 | 168.48 | 83.41 | 90
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Muktadaha zone I (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17207 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Rejuvenation Tube Well in connection to Accommodate FHTC at Pump House No.-I /II (Zone-I) under Muktadaha ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. (SM/09815) | Assistant Engineer | Junior Engineer | ORD/000650/2024-2025 | 2687/EMD | 20/11/2024 | 02/02/2025 | MA ANNAPURNA ENTERPRISE | 14.39 | 0 | 0 | 100
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Muktadaha zone I (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17207 | Augmentation | Supply, delivery, installation Commissioning of Electro Mechanical Equipments and allied works at Muktadaha zone I (PHASE-II) W/S Scheme Block- Karimpur-I under Eastern Mechanical Division, P.H.E, Dte. Dist. Nadia. SM/17207 | Assistant Engineer |  | ORD/000141/2025-2026 | 1142/EMD | 04/06/2025 | 02/09/2025 | J.D.J. ENTERPRISE (A UNIT OF JDJ TRADERS PVT LTD) | 32.62 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Muktadaha zone I (PHASE-II) IN Karimpur I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17207 | Augmentation | Laying of additional pipeline for providing balance FHTC and inerease functionality in Baro Jangal, Majlishpur, Basotipara Villages under Karimpur-I Block under Tehatta Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer Karimpur- II Block | ORD/000329/2025-2026 | .4686/4533/P-3/ND | 09/10/2025 | 07/01/2026 | JOY HIND TUBEWELL'S | 79.19 | 0 | 0 | 40
Total | [13 empty] | 328.18 | 168.48 | 51.34