## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONDA ZONE-I IN KRISHNAGAR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17208 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Sonada Zone-I Piped Water Supply Scheme Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001750/2023-2024 | 6361/EMD | 17/10/2023 | 16/11/2023 | A.G ENTERPRISE. | 41.9 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SONDA ZONE-I IN KRISHNAGAR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17208 | Augmentation | Renovation of AIRP (Semi-Gravity Type) of capacity 34 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Sonda Zone-I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer 3 | ORD/000082/2023-2024 | 2995/ND | 13/07/2023 | 01/04/2025 | TARUN KUMAR BHATTACHARYA | 62.48 | 0 | 0 | 40
Total | [13 empty] | 104.38 | 0 | 0