## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone III PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17209 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-III(Phase-II) under Teinpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. N.I.E.T No. 20 of EE / EMD of 2023-2024 (2023_PHED_554048_21) | Assistant Engineer | Junior Engineer | ORD/001907/2023-2024 | 6787/EMD | 30/11/2023 | 30/12/2023 | T.D.K. ENTERPRISE | 8.45 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone III PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17209 | Augmentation | Proposed Augmentation of Laying Rising Main System and Sinking of Replacement Tube Well at Head Work Site of Teinpur Zone-III [Phase-II] Ground Based Piped Water Supply Scheme. | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000520/2022-2023 | 1219/ND | 21/03/2023 | 20/05/2023 | JOY HIND TUBEWELL'S | 14.37 | 0 | 0 | 80
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone III PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17209 | Augmentation | Renovation of AIRP and Construction of Backwash chamber for AIRP at Head Work Site at Teinpur Zone-III PWSS under Nadia Division PHE Dte. Capacity- 40.30 cum/hr | Assistant Engineer | Junior Engineer Karimpur- II Block | ORD/000552/2023-2024 | 782/ND | 05/02/2024 | 05/05/2024 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 83.94 | 0 | 0 | 70
4 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Teinpur zone III PWSS (PHASE-II) IN Karimpur II BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17209 | Augmentation | Laying of 160 mm dia HDPE pipe line, 75 mm & 125 mm UPVC Pipe line for Augmentation of Rising Main System for distribution pipeline with interconnection along with road restoration at village Dogachhi, Block Karimpur-II under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer Nabadwip Block | ORD/000017/2025-2026 | 1803/ND | 22/04/2025 | 19/10/2025 | SUBHASH BOSE | 32.54 | 0 | 0 | 51
Total | [13 empty] | 139.3 | 0 | 0