## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Senpur (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17210 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Senpur (Phase-II) Piped Water Supply Scheme, Block: Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. |  |  | ORD/001751/2023-2024 | 6362/EMD | 17/10/2023 | 16/11/2023 | TARUN KUMAR BHATTACHARYA | 53.52 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Senpur (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17210 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 93.00 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Senpur PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000028/2023-2024 | 1786/ND | 20/04/2023 | 19/07/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 234.23 | 0 | 0 | 57
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Senpur (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17210 | Augmentation | WBSEDCL's Quotation of new service connection in Bulk contract demand to the Head Work site under Senpur W/S Scheme in Krishnagar-I Block , PHE Dte. Nadia (Application No.3004752314) |  |  | BILL/00749/2024-2025 | BP-53-24-25 | 21/06/2024 | 21/06/2024 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 3.47 | 0 | 0 | 0
Total | [13 empty] | 291.22 | 0 | 0