## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Subarnabihar ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17211 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 231 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Subarnabihar Zone I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000026/2023-2024 | 1784/ND | 20/04/2023 | 19/07/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 222.99 | 0 | 0 | 65
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR Subarnabihar ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17211 | Augmentation | Providing, installation and commissioning of Electro-Mechanical Equipment and allied works for Arsenic Removal Plant in connection to Accommodate FHTC under Subarna Behar ground water based water supply scheme under Block_ Krishnanagar-I Dist. - Nadia, under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001433/2024-2025 | 184/EMD | 29/01/2025 | 21/08/2025 | DAS ENTERPRISE (M) | 51.34 | 0 | 0 | 0
Total | [13 empty] | 274.32 | 0 | 0