## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PANSILA(PHASE-II) IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17213 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 93 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Pansila PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000085/2023-2024 | 2998/ND | 13/07/2023 | 11/10/2023 | TARUN KUMAR BHATTACHARYA | 90.1 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PANSILA(PHASE-II) IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17213 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under PANSILA W/S Scheme, Block-Nabadwip , Dist. - Nadia. NIET No.- 28 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer | ORD/001013/2022-2023 | 501/EMDdt.24.01.2023 | 16/03/2023 | 15/04/2023 | ASHOKE ADHIKARY | 15.59 | 4.75 | 30.43 | 100
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PANSILA(PHASE-II) IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17213 | Augmentation | Providing Electro-Mechanical Equipment and Allied Works for Arsenic Removal Plant at PANSILA (PHASE-II) Piped Water SupplyScheme, Block: NABADWIP, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001752/2023-2024 | 6363/EMD | 17/10/2023 | 01/09/2025 | GOENKA ENTERPRISE | 53.53 | 0 | 0 | 30
Total | [13 empty] | 159.22 | 4.75 | 2.98