## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17214 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 95 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at DAKSHIN JHITKAPOTA ZONE I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 5 | ORD/000086/2023-2024 | 2999/ND | 13/07/2023 | 27/06/2026 | B.M. ENGINEERING & CONSTRUCTION | 97.4 | 0 | 0 | 50
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17214 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) Piped Water Supply Scheme, Block: Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. |  |  | ORD/001754/2023-2024 | 6365/EMD | 17/10/2023 | 16/11/2023 | M.S. ENTERPRISE | 53.53 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17214 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. Augmentation to Accommodate FHTC under DAKSHIN JHITKIPOTA(Z-1) W/S Scheme, Block-Krishnagar-I, Dist. - Nadia. NIET No.- 33 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/001920/2022-2023 | 1176/EMD | 21/03/2023 | 20/04/2023 | SRI KRISHNA NIRMAN | 14.96 | 13.63 | 91.16 | 99
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR DAKSHIN JHITKAPOTA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17214 | Augmentation | Supplementary works to completion of ongoing FHTC-related work under Dakshin Jhitkipota (Zone-I) W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001716/2023-2024 | 754/EMSD-II | 09/10/2023 | 19/10/2023 | SRI KRISHNA NIRMAN | 0.63 | 0.63 | 99.82 | 100
Total | [13 empty] | 166.51 | 14.26 | 8.56