## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDAR KHOLA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17215 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I AND II under Bhandarkhola W/S Scheme, Block KrishnagarI, Dist. Nadia. NIET No. 23 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer | ORD/000885/2022-2023 | 153/EMD | 06/01/2023 | 05/02/2023 | P.K. ENTERPRISE | 15.11 | 13.41 | 88.77 | 65
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDAR KHOLA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17215 | Augmentation | Suplimentary works to completion of ongoing FHTC-related work at BHANDERKHOLA W/S Scheme (Block-Krishnagar-I) PHE Dte.,Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/001485/2023-2024 | 666/EMSD-II | 05/09/2023 | 20/09/2023 | P.K. ENTERPRISE | 0.69 | 0.64 | 92.97 | 100
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDAR KHOLA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17215 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 58 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bhanderkhola PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 3 | ORD/000084/2023-2024 | 2997/ND | 13/07/2023 | 11/10/2023 | TARUN KUMAR BHATTACHARYA | 87.75 | 15.34 | 17.48 | 68
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDAR KHOLA (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17215 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at BHANDAR KHOLA (Phase-II) Piped Water Supply Scheme Block_ KRISHNANAGAR-I Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001760/2023-2024 | 6371/EMD | 17/10/2023 | 01/09/2025 | GLACIER ENGINEERING CO. | 47.26 | 0 | 0 | 40
Total | [13 empty] | 150.81 | 29.39 | 19.49