## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PASCHIM BHATJUNGLA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17216 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Paschim Bhatjungla Zone-I (Phase-II) Piped Water Supply Scheme Block_ Krishnanagar-I Dist. - Nadia under EMD, PHE Dte. |  |  | ORD/001761/2023-2024 | 6372/EMD | 17/10/2023 | 16/11/2023 | MAHADEV ENTERPRISE | 53.53 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PASCHIM BHATJUNGLA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17216 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 104 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at PASCHIM BHATJUNGLA ZONE I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000027/2023-2024 | 1785/ND | 20/04/2023 | 11/04/2025 | B.M. ENGINEERING & CONSTRUCTION | 120.62 | 0 | 0 | 70
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR PASCHIM BHATJUNGLA ZONE-I (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17216 | Augmentation | Additional work of providing FHTC and additional work of Laying Distribution System in connection with Augmentation of Paschim Bhatjangla Zone-I PWSS within Krishnagar-I Block under RWS Nadia Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000073/2024-2025 | 4073/ND | 26/07/2024 | 12/01/2026 | SANDIP BISWAS | 148.49 | 0 | 0 | 70
Total | [13 empty] | 322.64 | 0 | 0