## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-II (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17217 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Ghoralia Zone-II (Phase-II) Piped Water Supply Scheme, Block: Santipur, Dist. Nadia Under EMD, PHE Dte. |  |  | ORD/001757/2023-2024 | 6367/EMD | 17/10/2023 | 16/11/2023 | ABHISEK ENGINEERING CONCERN | 42.09 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-II (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17217 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under ELANGI(Zone-II) & GHORALIA (Zone-II) W/S Scheme, Block- Chapra & Shantipurrespectively , Dist. - Nadia. NIET No.- 37 of EE/EMD of 2022-23 (Sl. No.- 05) |  |  | ORD/001157/2023-2024 | 1503EMD | 18/04/2023 | 18/05/2023 | MA ANNAPURNA ENTERPRISE | 11.19 | 0 | 0 | 60
3 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-II (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17217 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 28 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at GHORALIA ZONE-II PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer Santipur Block | ORD/000011/2023-2024 | 1805 / ND | 24/04/2023 | 23/07/2023 | MONDAL PRECISION PRIVATE LIMITED | 58.81 | 0 | 0 | 75
Total | [13 empty] | 112.09 | 0 | 0