## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-I (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17218 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under GHORALIA(Zone-1) W/S Scheme, Block- Shantipur , Dist. - Nadia. NIET No. 25 of EE/EMD of 2022-23 (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000904/2022-2023 | 414/EMDdt.20.01.23 | 17/03/2023 | 16/04/2023 | D.S. ENTERPRISE | 5.99 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-I (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17218 | Augmentation | Renovation of AIRP (Pressure Type) of capacity 95 Cu.m/hr at Head Work Site at GHORALIA ZONE- I PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer Ranaghat - I Block | ORD/000009/2023-2024 | 1804 / ND | 24/04/2023 | 23/07/2023 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 49.9 | 0 | 0 | 78
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-I (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17218 | Augmentation | Supply Delivery and installation of Changeover switch and Electrical wiring and other allied works at Ghoralia (Z-I) P/H- I W/S Scheme in the District of Nadia, Under EMSD-II PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002455/2023-2024 | 983/EMSD-II | 27/12/2023 | 06/01/2024 | D.S. ENTERPRISE | 0.6 | 0 | 0 | 100
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR GHORALIA ZONE-I (PHASE-II) IN SANTIPUR BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17218 | Augmentation | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Ghoralia Zone-I (Phase-II) Piped Water Supply Scheme, Block: Santipur, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001758/2023-2024 | 6368/EMD | 17/10/2023 | 01/12/2025 | ESENCE ENGINEERING CONCERN | 53.51 | 0 | 0 | 100
Total | [13 empty] | 110 | 0 | 0