## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANKAR DHOPADI IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17219 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 29 Cu.m/hr and Construction of Backwash chamber for AIRP at Head Work Site at Bankar Dhopadi PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000081/2023-2024 | 2994/ND | 13/07/2023 | 11/10/2023 | TARUN KUMAR BHATTACHARYA | 70.11 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANKAR DHOPADI IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17219 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BANKER DHOPADI W/S Scheme, Block- Nabadwip , Dist. - Nadia. NIET NO. 28 OF EE/EMD OF 2022-23 (SL. NO. 02) | Assistant Engineer | Junior Engineer | ORD/001256/2022-2023 | 813/EMDdt.16.02.2023 | 16/03/2023 | 15/04/2023 | UTTAM KUMAR CHATTERJEE | 14.15 | 0 | 0 | 100
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BANKAR DHOPADI IN NABADWIP BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17219 | Augmentation | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at Bankar Dhopadi Piped Water Supply Scheme Block_ Nabadwip Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001762/2023-2024 | 6373/EMD | 17/10/2023 | 01/04/2025 | AHALYA ENGINEERING WORKS | 42.1 | 0 | 0 | 0
Total | [13 empty] | 126.35 | 0 | 0