## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KULGACHHI (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17232 | Augmentation | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at KULGACHI (Phase-II) Piped Water Supply Scheme, Block: Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001753/2023-2024 | 6364/EMD | 17/10/2023 | 16/11/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 49.3 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KULGACHHI (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17232 | Augmentation | Renovation of AIRP (Gravity Type) of capacity 67 Cu.m/hr at Head Work Site at Kulgachi PWSS under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000005/2023-2024 | 1599/ND | 10/04/2023 | 31/03/2025 | B.M. ENGINEERING & CONSTRUCTION | 72.07 | 0.65 | 0.9 | 100
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KULGACHHI (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17232 | Augmentation | Supply, Delivery Installation of Submersible Pumping Machinery alongwith allied Electro Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc. rejuvenation to Accommodate FHTC at Pump House No. I and II under Kulgachi WS Scheme, Block KrishnagarI, Dist. Nadia. NIET No.- 23 of EE/EMD of 2022-23 (Sl. No.-09) |  |  | ORD/002969/2022-2023 | 158EMD,Dt.06.01.23 | 27/03/2023 | 26/04/2023 | ABHISEK ENGINEERING CONCERN | 15.5 | 1.31 | 8.48 | 100
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KULGACHHI (PHASE-II) IN KRISHNAGAR-I BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17232 | Augmentation | Supplementary works to completion of ongoing FHTC-related work under Kulgachi W/S Scheme (Block - Krishnagar-I), PHE Dte., Dist.-Nadia. | Assistant Engineer | Junior Engineer | ORD/002483/2023-2024 | 956/EMSD-II | 26/12/2023 | 05/01/2024 | ABHISEK ENGINEERING CONCERN | 0.69 | 0.69 | 100 | 100
Total | [13 empty] | 137.56 | 2.65 | 1.93