## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Nakashipara | Nadia Division | Gotpara Piped Water Supply Scheme | SM/17685 | New | Route Survey, Design Drawing & DPR preparation for Gotpara water supply scheme under Debagram Sub- Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000319/2023-2024 | 319/DSD | 17/08/2023 | 01/09/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.28 | 2.28 | 100 | 100
2 | NADIA | Nakashipara | Eastern Mechanical | Gotpara Piped Water Supply Scheme | SM/17685 | New | Providing And Installation of Electro_Mechanical Equipments and Allied Works for Arsenic Removal Plant at GOTPARA Piped Water Supply Scheme Block_ Nakashipara Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer |  | ORD/002821/2023-2024 | 811/EMD | 11/03/2024 | 10/04/2024 | R.N.S. TRADING | 42.44 | 0 | 0 | 0
3 | NADIA | Nakashipara | Nadia Division | Gotpara Piped Water Supply Scheme | SM/17685 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of capacity 10 m3/hr at Gotpara Water Supply Scheme within Nakashipara Block under Debagram Sub-Divn. under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000790/2023-2024 | 1901/ND | 15/03/2024 | 11/09/2024 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 132.89 | 0 | 0 | 0
4 | NADIA | Nakashipara | Nadia Division | Gotpara Piped Water Supply Scheme | SM/17685 | New | Sinking of 1 No. 250mm. X 150mm. Dia 200 Mtr. deep Tube Well by Direct Rotary Rig Method using UPVC pipe having 250 mm Dia 48 Mtr. Long Housing Pipe & 150 mm. Dia Well Pipe & Deep Well Screen Pipe (RDS Strainer) at Gotpara Pipe Water Supply Scheme, at Nakashipara Block under Debagram Sub-Division under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000387/2023-2024 | 5117/ND | 17/11/2023 | 17/12/2023 | B.M. ENGINEERING & CONSTRUCTION | 11.88 | 9.95 | 83.75 | 100
5 | NADIA | Nakashipara | Nadia Division | Gotpara Piped Water Supply Scheme | SM/17685 | New | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 276/ND | 11/01/2024 | 11/01/2024 | Resource Division | 4.29 | 0 | 0 | 0
6 | NADIA | Nakashipara | Eastern Mechanical | Gotpara Piped Water Supply Scheme | SM/17685 | New | Quotation for New Connection at PH-I under Goat Para W/S Scheme under EMSD-III,PHE Dte. |  |  | BILL/01079/2024-2025 | BP-68-24-25 | 15/07/2024 | 15/07/2024 | WBSEDCL BETHUADAHARI (NORTH) CCC | 9.3 | 0 | 0 | 0
Total | [13 empty] | 203.08 | 12.24 | 6.02