## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Kaliganj | Nadia Division | Noachar Piped Water Supply Scheme | SM/17686 | New | Route Survey, Design Drawing & DPR preparation for Noachar water supply scheme under Debagram Sub- Division under Nadia Division, PHE Dte. | Assistant Engineer |  | ORD/000320/2023-2024 | 321/DSD | 17/08/2023 | 01/09/2023 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2.05 | 2.05 | 100 | 100
2 | NADIA | Kaliganj | Nadia Division | Noachar Piped Water Supply Scheme | SM/17686 | New | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 3642/ND | 16/08/2023 | 16/08/2023 | Resource Division | 1.43 | 0 | 0 | 0
3 | NADIA | Kaliganj | Nadia Division | Noachar Piped Water Supply Scheme | SM/17686 | New | Material Requisition To Resource Division |  |  | RTOR000112/2023-2024 | 4222/ND | 19/09/2023 | 19/09/2023 | Resource Division | 1.64 | 0 | 0 | 0
4 | NADIA | Kaliganj | Nadia Division | Noachar Piped Water Supply Scheme | SM/17686 | New | Construction of 10.00 cum/hr capacity Arsenic-Cum-Iron Removal Plant (AIRP) at Noachar PWSS including 3 Months Trial Run & 3 Years O&M under Kaliganj Block under Nadia Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000738/2023-2024 | 1494/ND | 04/03/2024 | 31/08/2024 | SATYABRATA CHAKRABORTY | 133.17 | 0 | 0 | 0
5 | NADIA | Kaliganj | Nadia Division | Noachar Piped Water Supply Scheme | SM/17686 | New | Sinking of 1 No. 250mm. X 150mm. Dia 200 Mtr. deep Tube Well by Direct Rotary Rig Method using UPVC pipe having 250 mm Dia 48 Mtr. Long Housing Pipe & 150 mm. Dia Well Pipe & Deep Well Screen Pipe (RDS Strainer) at Noachar Pipe Water Supply Scheme, at Kaliganj Block under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000388/2023-2024 | 5118/ND | 17/11/2023 | 17/12/2023 | B.M. ENGINEERING & CONSTRUCTION | 11.88 | 8.41 | 70.79 | 100
6 | NADIA | Kaliganj | Nadia Division | Noachar Piped Water Supply Scheme | SM/17686 | New | Construction of Jhama Bats Road for the approach way to headwork site of Noachar water supply scheme under Kalyani Sub Division I under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000522/2023-2024 | 105/KLYSD-I | 25/01/2024 | 24/02/2024 | CHOWDHURY & CO. | 4.92 | 4.89 | 99.45 | 100
7 | NADIA | Kaliganj | Nadia Division | Noachar Piped Water Supply Scheme | SM/17686 | New | Laying distribution system for providing FHTC at Noarchar Mouza in connection with Augmentation of Ground Based Water Supply Scheme at Noachar to accommodate FHTC under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000779/2023-2024 | 1764/ND | 12/03/2024 | 26/04/2024 | CHOWDHURY & CO. | 9.73 | 9.44 | 97.05 | 100
8 | NADIA | Kaliganj | Nadia Division | Noachar Piped Water Supply Scheme | SM/17686 | New | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 275/ND | 11/01/2024 | 11/01/2024 | Resource Division | 2.33 | 0 | 0 | 0
9 | NADIA | Kaliganj | Eastern Mechanical | Noachar Piped Water Supply Scheme | SM/17686 | New | Quotation for new service connection at Nayachar water supply scheme. |  |  | BILL/00800/2024-2025 | BP-58-24-25 | 02/07/2024 | 02/07/2024 | WBSEDCL DAINHAT CCC | 3.13 | 0 | 0 | 0
10 | NADIA | Kaliganj | Nadia Division | Noachar Piped Water Supply Scheme | SM/17686 | New | Noachar Piped Water Supply in Kaliganj Block of Nadia District under Nadia Division P.H.Engineering Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000093/2023-2024 | 3023/ND | 14/07/2023 | 04/04/2025 | CHOWDHURY & CO. | 64.66 | 59.5 | 92.02 | 100
11 | NADIA | Kaliganj | Eastern Mechanical | Noachar Piped Water Supply Scheme | SM/17686 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I under Noachar ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. [SM/17686] | Assistant Engineer | Junior Engineer | ORD/000337/2024-2025 | 2152/EMD | 30/08/2024 | 01/06/2025 | C.M.S. ENGINEERING CONCERN. | 11.49 | 9.83 | 85.52 | 80
Total | [13 empty] | 246.43 | 94.12 | 38.19