## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGULA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17688 | Augmentation | Sinking of Rig Bored Tubewell (Replacement) 300mm. x 200 mm. dia. 200 mtr deep by Direct Rotary method using UPVC pipe under Augmentation of different Water Supply Scheme (Phase-II) in Hanskhali Block, under Ranaghat Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000529/2022-2023 | 1272/ND | 23/03/2023 | 22/05/2023 | AUXILIARY TUBEWELL DRILLERS | 48.99 | 0 | 0 | 66
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BAGULA ZONE-I (PHASE-II) IN HANSKHALI BLOCK OF NADIA DISTRICT UNDER NADIA DIVISION, PHE DTE. | SM/17688 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation Tube Well in connection to Accommodate FHTC at Pump House No.-I, Zone-I(Phase-II) under Bagula ground water based water supply scheme under Block_ Hanskhali Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001774/2023-2024 | 6398/EMD | 30/10/2023 | 29/11/2023 | A.K. ENTERPRISE | 12.6 | 0 | 0 | 100
Total | [13 empty] | 61.58 | 0 | 0