## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-11-2023 to 31-01-2024 | Assistant Engineer | Junior Engineer 2 | ORD/000404/2023-2024 | 1207/KLYSD-I | 17/11/2023 | 17/02/2024 | CONSTRUCTURE | 4.76 | 4.76 | 100 | 100
2 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Continuation work order for Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. for the period from 01.08.2023 to 31.10.2023 | Assistant Engineer |  | ORD/000177/2023-2024 | 791/KLYSD-I | 27/07/2023 | 27/10/2023 | CONSTRUCTURE | 0.95 | 0.05 | 5.51 | 100
3 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Fund Requisition for ASHA incentive for Water Sample testing by FTK Phase-II Jan-23 to April-23. |  |  | BILL/00379/2023-2024 | 165/PFMS | 11/07/2023 | 11/07/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 37.28 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Fund Requisition for ASHA Incentive for Water Sample Testing by FTK Phase-II for the period from 01/05/2023 to 30/09/2023. |  |  | BILL/00855/2023-2024 | 383/PFMS | 04/11/2023 | 04/11/2023 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 31.9 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-05-2024 to 31-07-2024 | Assistant Engineer | Junior Engineer 2 | ORD/000002/2024-2025 | 788/KlySD-I | 30/04/2024 | 31/07/2024 | CONSTRUCTURE | 4.76 | 3.07 | 64.49 | 100
6 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-02-2024 to 30-04-2024 | Assistant Engineer | Junior Engineer 2 | ORD/000713/2023-2024 | 77/KLYSD-I | 22/01/2024 | 22/04/2024 | CONSTRUCTURE | 4.76 | 3.26 | 68.45 | 60
7 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-08-2024 to 31-10-2024 | Assistant Engineer | Junior Engineer 2 | ORD/000259/2024-2025 | 1159/KlySD-I | 31/07/2024 | 31/10/2024 | CONSTRUCTURE | 4.76 | 1.92 | 40.36 | 48
8 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-11-2024 to 31-01-2025 | Assistant Engineer | Junior Engineer 2 | ORD/000370/2024-2025 | 1577/KlySD-I | 29/10/2024 | 29/01/2025 | CONSTRUCTURE | 4.76 | 3.84 | 80.55 | 100
9 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Bill for Requisition of ASHA incentive for Water Sample Testing by FTK Phase-III( January 2024 to August 2024 ), Name of the Account - District Health & Family Welfare Samity, Nadia Bank & Branch Name - PNB, Krishnagar Account Number - 0215010438529 IFSC Code - PUNB0021520 |  |  | BILL/00538/2024-2025 | 324/PFMS | 05/10/2024 | 05/10/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 22.57 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Fund requirement for ASHA incentive for Water Sample testing by FTK Phase-II ( Oct-23 to Nov-23) |  |  | BILL/00178/2024-2025 | 117/PFMS | 17/07/2024 | 17/07/2024 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 3.25 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-08-2025 to 31-10-2025. | Assistant Engineer | Junior Engineer 2 | ORD/000239/2025-2026 | 1522/KlySD-I | 01/08/2025 | 01/11/2025 | CONSTRUCTURE | 4.76 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-02-2025 to 30-04-2025 | Assistant Engineer | Junior Engineer 2 | ORD/000752/2024-2025 | 168/KlySD-I | 28/01/2025 | 27/04/2025 | CONSTRUCTURE | 4.76 | 0 | 0 | 82
13 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Continuation of Uploading of FTK testing data at Water Quality Dash Board in Nadia District under Nadia Division, PHE Dte. W.e.f. 01-05-2025 to 31-07-2025 (Three months) | Assistant Engineer | Junior Engineer 2 | ORD/000032/2025-2026 | 809/KlySD-I | 30/04/2025 | 31/07/2025 | CONSTRUCTURE | 4.76 | 0 | 0 | 100
14 | NADIA |  | Nadia Division | Collection, Testing & Uploading Charges of Drinking Water Samples through Field Test Kits (FTKs) In Nadia District (Phase-II) Related to Water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission | SM/18273 | Support-WQMSP | Placement of fund for ASHA incentive for Water Sample testing by FTK from Sep-2024 to Mar-2025 (Phase III & Phase IV) |  |  | BILL/00230/2025-2026 | 94/JJM | 10/07/2025 | 10/07/2025 | DISTRICT HEALTH & FAMILY WELFARE SAMITI | 2.15 | 0 | 0 | 0
Total | [13 empty] | 136.19 | 16.9 | 12.41