## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000189/2022-2023 | 147/ND | 06/01/2023 | 06/01/2023 | Resource Division | 1858.7 | 0 | 0 | 0
2 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for service connection charge and security deposit for new power connection at Majhergram OHR Site under Northern Sector, Part-II SWB Project , PHE Dte. |  |  | BILL/01578/2024-2025 | BP-109-24-25 | 09/09/2024 | 09/09/2024 | WBSEDCL BETHUADAHARI (NORTH) CCC | 3.86 | 0 | 0 | 0
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for New power connection at Gopalpur OHR ( Zone-II/B) under Northern Sector, Part-II SWB Project. |  |  | BILL/01327/2024-2025 | BP-75-24-25 | 30/07/2024 | 30/07/2024 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-135 |  |  | BILL/00514/2024-2025 | 308/PFMS | 02/10/2024 | 02/10/2024 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 12.52 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for new service connection and security deposit at Kalibus OHR (Zone-VII/B) under Northern Sector, Part-II SWB Project,PHE Dte. |  |  | BILL/01577/2024-2025 | BP-108-24-25 | 09/09/2024 | 09/09/2024 | WBSEDCL BETHUADAHARI CCC | 3.95 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for service connection charge and security deposit for new power connection at Bilkumarik OHR(Zone-VI/B) Site under Northern Sector, Part-II SWB Project , PHE Dte. |  |  | BILL/01580/2024-2025 | BP-111-24-25 | 09/09/2024 | 09/09/2024 | WBSEDCL DEBOGRAM CCC | 2.64 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for earnest money deposit for Bulk power supply at Nakashipara GLR project. |  |  | BILL/00384/2024-2025 | BP-23-24-25 | 21/05/2024 | 21/05/2024 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 0.05 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for New power connection at Gachha OHR ( Zone-IX/B) under Northern Sector, Part-II SWB Project. |  |  | BILL/01326/2024-2025 | BP-76-24-25 | 30/07/2024 | 30/07/2024 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for New HT Bulk connection at Nakashipara GLR Project under Easter Mechanical Division, Dist-Nadia |  |  | BILL/01150/2024-2025 | BP-69-24-25 | 26/07/2024 | 26/07/2024 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 39.38 | 0 | 0 | 0
10 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for New power connection at Digha OHR ( Zone-VIII/C) under Northern Sector, Part-II SWB Project. |  |  | BILL/01329/2024-2025 | BP-77-24-25 | 30/07/2024 | 30/07/2024 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0 | 0
11 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for service connection charge and security deposit for new power connection at Sonadanga OHR Site under Northern Sector, Part-II SWB Project , PHE Dte. |  |  | BILL/01579/2024-2025 | BP-110-24-25 | 09/09/2024 | 09/09/2024 | WBSEDCL BETHUADAHARI (NORTH) CCC | 3.74 | 0 | 0 | 0
12 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Quotation for New power connection at Teghari OHR ( Zone-VIII/B) under Northern Sector Part-II SWB Project. |  |  | BILL/01330/2024-2025 | BP-74-24-25 | 30/07/2024 | 30/07/2024 | MURAGACHA DHARMADA CCC | 0.3 | 0 | 0 | 0
13 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Augmentation of pumping machinery and electrical equipments at WTP along with implementation of SCADA System for surface water based water supply scheme, Arsenic affected area, Northern Sector, Part-II (Block - Nakasipara) in the district of Nadia, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/001687/2023-2024 | 6261/EMD | 10/10/2023 | 01/07/2025 | MACHINE SUPLIERS SYNDICATE (P) LTD. | 234.62 | 0 | 0 | 40
14 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Providing Axially Split Centrifugal Pumping machinery for GLR along with secondary disinfection arrangement for surface water based water supply scheme, Arsenic Affected Area, Northern Sector, Part-II (Block - Nakasipara) in the district of Nadia, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/001690/2023-2024 | 6264/EMD | 10/10/2023 | 31/10/2025 | WEST BENGAL ENGINEERING CO. | 276.03 | 122.7 | 44.45 | 60
15 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Augmentation of Water Treatment Plant (augmented to 34.52 MLD), repairing & renovation of Rising Main from WTP to different ESR and zonal OHR and soil test, design & construction of Boosting Station along with allied civil work including 6 (six) months trial run for Surface Water Based Piped Water Supply Scheme for Northern Sector, Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2,Junior Engineer 3 | ORD/000366/2023-2024 | 4773/ND | 16/10/2023 | 01/11/2025 | GB CONSTRUCTION | 6109.51 | 4711.68 | 77.12 | 9
16 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 16/03/2025 | BIBHAS PAL | 96.01 | 5.93 | 6.17 | 30
17 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 01/10/2025 | UMWELT ENGINEER PVT LTD | 1506.76 | 0 | 0 | 52
18 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Jack pushing & pipe crossing work at Khidirpur Mouza under Northern Sector Part-II under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000003/2025-2026 | 1646/ND | 07/04/2025 | 06/07/2025 | MONDAL ENTERPRISE | 97.53 | 0 | 0 | 1
19 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART II) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18387 | Augmentation | Additional Work for Installation of SCADA System in connection with Augmentation of Surface Water Based Piped Water Supply Scheme for Northern Sector Part-II in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3 | ORD/000141/2025-2026 | 3447/ND | 23/07/2025 | 20/11/2025 | GBC INFRASTRUCTURE PRIVATE LIMITED | 732.35 | 0 | 0 | 15
Total | [13 empty] | 10978.87 | 4840.31 | 44.09