## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000170/2022-2023 | 131/ND | 06/01/2023 | 06/01/2023 | Resource Division | 1214.5 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Collection of Household data through mobile app for FHTC Connection of Surface Based PWSS for Northern Sector (Part-I) (Zone-IXA to Zone-IXB) under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000353/2023-2024 | 913/KLYSD-I | 29/08/2023 | 29/02/2024 | TECHVISION | 0.97 | 0.97 | 100 | 100
3 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | New Service connection and security deposit for Debagram (Zone- 5B) OHR site. |  |  | BILL/01772/2024-2025 | BP-147-24-25 | 28/10/2024 | 28/10/2024 | WBSEDCL DEBOGRAM CCC | 3.81 | 0 | 0 | 0
4 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | New Service connection and security deposit for Ghoraikhetra (zone- 4B) OHR site. |  |  | BILL/01774/2024-2025 | BP-149-24-25 | 28/10/2024 | 28/10/2024 | WBSEDCL DEBOGRAM CCC | 3.42 | 0 | 0 | 0
5 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Quotation for new service connection charges and security deposit for Dakshin Hazrapota OHR site. |  |  | BILL/01770/2024-2025 | BP-145-24-25 | 28/10/2024 | 28/10/2024 | WBSEDCL.MATIARY.CCC | 11.45 | 0 | 0 | 0
6 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | New Service connection and security deposit for Asachiya (Zone- 3B) OHR site. |  |  | BILL/01773/2024-2025 | BP-148-24-25 | 28/10/2024 | 28/10/2024 | WBSEDCL DEBOGRAM CCC | 3.65 | 0 | 0 | 0
7 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Quotation for new service connection charges and security deposit for Bathangachi OHR (Zone-6B) site. |  |  | BILL/01771/2024-2025 | BP-146-24-25 | 28/10/2024 | 28/10/2024 | WBSEDCL.PALASSEY.CCC | 4.28 | 0 | 0 | 0
8 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Service connection charges and Security deposit for new bulk power supply to Kaliganj GLR, Nadia, Pin code- 741136. |  |  | BILL/01309/2024-2025 | BP-79-24-25 | 02/08/2024 | 02/08/2024 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 39.52 | 0 | 0 | 0
9 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Quotation for new service connection charges and security deposit for Juranpur OHR site. |  |  | BILL/01769/2024-2025 | BP-144-24-25 | 28/10/2024 | 28/10/2024 | WBSEDCL.MATIARY.CCC | 3.86 | 0 | 0 | 0
10 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Quotation for new service connection and security deposit for Chhota chandghar OHR (Zone-9B) site |  |  | BILL/01776/2024-2025 | BP-151-24-25 | 28/10/2024 | 28/10/2024 | WBSEDCL.PALASSEY.CCC | 7.98 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-136 |  |  | BILL/00516/2024-2025 | 307/PFMS | 02/10/2024 | 02/10/2024 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 6.59 | 0 | 0 | 0
12 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Quotation for earnest Money deposit for bulk power supply for Kaliganj GLR Project. |  |  | BILL/00383/2024-2025 | BP-24-24-25 | 21/05/2024 | 21/05/2024 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 0.05 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-112 |  |  | BILL/00515/2024-2025 | 306/PFMS | 02/10/2024 | 02/10/2024 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 4.99 | 0 | 0 | 0
14 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Quotation for new service connection and security deposit for Bhurulia OHR (Zone- 7B) site, plaseey. |  |  | BILL/01775/2024-2025 | BP-150-24-25 | 28/10/2024 | 28/10/2024 | WBSEDCL.PALASSEY.CCC | 4.47 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 30.06 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 19 Nos. distribution zone for Northern Sector, Part-I in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1,Junior Engineer 2 | ORD/000108/2023-2024 | 3141/ND | 21/07/2023 | 25/07/2026 | G.B. CONSTRUCTION & UMWELT JV | 16444.17 | 2686.7 | 16.34 | 47
16 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Augmentation of pumping machinery and electrical equipments at Intake, WTP alongwith implementation of SCADA System for surface water based water supply scheme, Arsenic affected area, Northern Sector, Part-I (Block - Kaliganj) in the district of Nadia, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/001689/2023-2024 | 6263/EMD | 10/10/2023 | 01/06/2025 | ORIENTAL ENGINEERING CO. | 308.87 | 0 | 0 | 25
17 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Providing Axially Split Centrifugal Pumping machinery for GLR alongwith secondary disinfection arrangement for surface water based water supply scheme, Arsenic Affected Area, Northern Sector, Part-I (Block - Kaliganj) in the district of Nadia, P. H. E. Dte. | Assistant Engineer | Junior Engineer | ORD/001688/2023-2024 | 6262/EMD | 10/10/2023 | 01/06/2025 | ORIENTAL ENGINEERING CO. | 271.65 | 0 | 0 | 25
18 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Additional Work for Ground Improvement of OHR foundation, renovation of OHR & other allied works of Northern Sector Part-I, Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000185/2024-2025 | 6095/ND | 19/09/2024 | 17/05/2025 | UMWELT ENGINEER PVT LTD | 225.66 | 127.18 | 56.36 | 75
19 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Additional Work for Augmentation of Surface Water Based Piped Water Supply Scheme for Different Zones (Northern Sector Part-I) , ZONE V / A (Northern Sector Part-I) in Kaliganj Block & Different Zones (Northern Sector Part-II) in Nakashipara Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000232/2024-2025 | 6464/ND | 01/10/2024 | 01/10/2026 | UMWELT ENGINEER PVT LTD | 1506.76 | 470.02 | 31.19 | 52
20 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART I) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18388 | Augmentation | Refixing of Existing FHTC with Ferrule Connection at Surface Water Based W/S Scheme for Arsenic Affected Areas of Nadia District (Northern Sector Part-I) under Nadia Division, PHED. | Assistant Engineer | Junior Engineer 1 | ORD/000504/2023-2024 | 559/ND | 25/01/2024 | 19/04/2025 | UMWELT ENGINEER PVT LTD | 207.02 | 145.66 | 70.36 | 51
Total | [13 empty] | 20273.68 | 3430.53 | 16.92