## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Augmentation of Intake, Water Treatment Plant (augmented to 15.96 MLD) & Rising Main for Surface Water Based piped Water Supply Scheme including augmentation, laying & construction of various components like Laying Distribution System, OHR, FHTC, Repairing of pump house, staff quarter, chlorination room, boundary wall etc., approach road & road restoration etc. for 8 Nos. distribution zone for Northern Sector, Part-III in Krishnagar-II & Nabadwip Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 3,Junior Engineer 4,Junior Engineer 5 | ORD/000196/2023-2024 | 3537/ND | 11/08/2023 | 01/10/2026 | RMN-SREE SUBHA JOINT VENTURE | 9470.81 | 1032.22 | 10.9 | 20
2 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000166/2022-2023 | 88/ND | 05/01/2023 | 05/01/2023 | Resource Division | 1297.82 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Continuation of Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000685/2024-2025 | 3957/ND | 19/07/2024 | 16/03/2025 | BIBHAS PAL | 96.01 | 0 | 0 | 30
4 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Hiring of 1 (One) no Diesel Luxury Taxi/ Maxi Cab/ Motor Cab on daily basis under monthly hiring category for the office of the Assistant Engineer, Krishnagar Sub Division, PHE Dte for supervision of JJM works for the period of 01/01/2025 to 31/12/2025 | Assistant Engineer | Junior Engineer 3 | ORD/000706/2024-2025 | 2666/KSD | 31/12/2024 | 31/12/2025 | AVINABA ENGINEERING CONCERN | 4.8 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-111 |  |  | BILL/00517/2024-2025 | 309/PFMS | 02/10/2024 | 02/10/2024 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 8.94 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Payment to Ministry of Railway regarding railway crossing, Application ID- ER-SDAH-2024-WL-134 |  |  | BILL/00518/2024-2025 | 310/PFMS | 02/10/2024 | 02/10/2024 | MINISTRY OF RAILWAYS, EASTERN RAILWAY, SEALDAH DIVISION | 5.09 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Additional Work for lnstallation of SCADA system in connection with Augmentation of surface water Based Piped water supply Scheme for Northern Sestor Part-l in Kaliganj Block of Nadia District under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000236/2025-2026 | 3829/ND | 13/08/2025 | 08/08/2026 | UMWELT ENGINEER PVT LTD | 736.14 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Supply of Document for Way leave Permission from Eastern Railway Authority at 2 nos of locations in between Bahadurpur Stn. - Dhubulia Stn. And Krishnagar Stn. - Bahadurpur Stn. Under Surface water based PWSS at Northern sector Part III under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 1 | ORD/000027/2025-2026 | 800/KlySD-I | 30/04/2025 | 30/05/2025 | SUMAN CHAKRABORTY | 3.84 | 0 | 0 | 100
9 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Supply of Document for Way leave Permission from Eastern Railway Authority at 2 nos of locations in between Shantipur Stn. - Dignagar Stn. And Majhdia Stn. - Banpur Stn. Under Ground water based PWSS at Dignagar & Tungi under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 1 | ORD/000028/2025-2026 | 801/KlySD-I | 30/04/2025 | 30/05/2025 | SUMAN CHAKRABORTY | 3.84 | 0 | 0 | 100
10 | NADIA |  | Nadia Division | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Supply of Document for Way leave Permission from Eastern Railway Authority at 2 nos of locations in between Shantipur Stn. - Dignagar Stn. And Majhdia Stn. - Banpur Stn. Under Ground water based PWSS at Dignagar & Tungi under Nadia Division, PHE Dte, Kalyani, Nadia. | Assistant Engineer | Junior Engineer 1 | ORD/000026/2025-2026 | 799/KlySD-I | 30/04/2025 | 30/05/2025 | SUMAN CHAKRABORTY | 3.84 | 0 | 0 | 100
11 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Quotation charges for new power connection and Security Deposit for Tatla OHR(Khejuri,Zone-IV/B) under Northern Sector Part-III(belpukur) ,PHE Dte.,Nadia. |  |  | BILL/02588/2024-2025 | BP-244 | 04/02/2025 | 04/02/2025 | W.B.S.E.D.C.L (DHUBULIA CCC) | 4.84 | 0 | 0 | 0
12 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Quotation charges for new HT Bulk power connection and Security Deposit for Harindanga GLR under Northern Sector part-III(Belpukur),PHE Dte.,Nadia. |  |  | BILL/02587/2024-2025 | BP-243 | 04/02/2025 | 04/02/2025 | WBSEDCL (RM NADIA REGIONAL OFFICE) | 25.1 | 0 | 0 | 0
13 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Quotation charges for new service connection and security deposit at Sadhanpara OHR(Zone-I/B) under Northern Sector Part-III(Belpukur),PHE dte., Nadia |  |  | BILL/02515/2024-2025 | BP-230 | 22/01/2025 | 22/01/2025 | MURAGACHA DHARMADA CCC | 0.36 | 0 | 0 | 0
14 | NADIA |  | Eastern Mechanical | AUGMENTATION OF INTAKE, WTP & RISING MAIN FOR SURFACE WATER-BASED PIPED WATER SUPPLY SCHEME FOR ARSENIC-AFFECTED AREAS NORTHERN SECTOR (PART III) OF NADIA DISTRICT TO ACCOMMODATE FHTC UNDER NADIA DIVISION | SM/18389 | Augmentation | Quotation charges and Security deposit for new service connection at Mayakol OHR(Zone-III/B) under Northern Sector Part-III (Belpukur) SWB W/S Scherme, Nadia |  |  | BILL/02514/2024-2025 | BP-229 | 22/01/2025 | 22/01/2025 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 5.03 | 0 | 0 | 0
Total | [13 empty] | 11666.45 | 1032.22 | 8.85