## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Continuation of work order for Arrear Payment for enhanced monthly remuneration of laboratory personnel of Nadia District Water Testing Laboratory at W.T.P, Haringhata under Kalyani Sub-Division-1 PH Engineering Dte in the district of Nadia. W.e.f. 01/09/2023 to 30/11/2023 (Three months) | Assistant Engineer | Junior Engineer 2 | ORD/000285/2023-2024 | 909/KLYSD-I | 28/08/2023 | 28/11/2023 | M/S S.K. ENTERPRISE | 0.84 | 0.21 | 25.58 | 100
2 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment for enhancement of monthly remuneration of 02 Nos personnel (State Lab Sr. Chemist, State Lab Chemist/ Bacteriologest, ) at 01 Nos State Laboratory under Nadia Division, PHE Dte. on contractual basis. | Assistant Engineer |  | ORD/000354/2023-2024 | 886/KLYSD-I | 21/08/2023 | 28/08/2023 | M/S S.K. ENTERPRISE | 0.69 | 0.69 | 100 | 100
3 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Continuation of work order for Monthly remuneration of one(01) no of lab assistant, one(01) no of Lab attendant and one(01) no sampling assistant through agency at Habibpur SD lab & Nadia District Laboratory under Nadia Division, PHE Dte. W.e.f. 01/09/2023 to 30/11/2023 (Three months) | Assistant Engineer | Junior Engineer 2 | ORD/000384/2023-2024 | 933/KLYSD-I | 31/08/2023 | 30/11/2023 | M/S S.K. ENTERPRISE | 0.75 | 0.34 | 44.83 | 100
4 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment for enhancement of monthly remuneration of 01 Nos personnel(State Lab Sr.Chemist) at'Kalyani State Referral Laboratory"under Nadia division,PHE Dte.on contractual basis W.e.f.01.09.2023 to 30.09.2023 | Assistant Engineer | Junior Engineer 2 | ORD/000413/2023-2024 | 1202/KLYSD-I | 10/11/2023 | 10/12/2023 | M/S S.K. ENTERPRISE | 0.18 | 0.18 | 100 | 100
5 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR NGO LAB FOR THE MONTH OF NOV-23. |  |  | BILL/00951/2023-2024 | 424/PFMS | 13/12/2023 | 13/12/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BARA ANDULIA MOHILA SAMITY NGO LAB FOR THE MONTH OF NOV-23. |  |  | BILL/00953/2023-2024 | 426/PFMS | 13/12/2023 | 13/12/2023 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINOY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF NOV-23. |  |  | BILL/00954/2023-2024 | 427/PFMS | 13/12/2023 | 13/12/2023 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR WBCADC RANAGHAT-II NGO LAB FOR THE MONTH OF NOV-23. |  |  | BILL/00950/2023-2024 | 423/PFMS | 13/12/2023 | 13/12/2023 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMITY NGO LAB FOR THE MONTH OF NOV-23. |  |  | BILL/00952/2023-2024 | 425/PFMS | 13/12/2023 | 13/12/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Operational Charges of NGO Managed Laboratory for Bara Andulia Mohila Samity. |  |  | BILL/00976/2023-2024 | 449/PFMS | 22/12/2023 | 22/12/2023 | BARA ANDULIA MAHILA SAMITY | 0.4 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of 25 Nos personnel (Sub-District Chemist, Sub- District Bacteriologest, Sub-District Lab-Assistant, Sub-District Sampling Assistant, Sub- District Lab attendant and District Chemist, District Bacteriologest, District Lab-Assistant, District Sampling Assistant, District Lab attendant ) at 04 Nos Sub-District Laboratories & 01 District Laboratory under Nadia Division, PHE Dte. on contractual basis with effecct from 01-09-2023 to 31-08-2024. | Assistant Engineer | Junior Engineer 2 | ORD/000280/2023-2024 | 3841/ND | 28/08/2023 | 27/08/2024 | CLIFFORD FACILITY SERVICES PVT. LTD | 50.56 | 43.18 | 85.41 | 30
12 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Remuneration of State Water Testing laboratory personnel for the month of October of 2022-2023 at W.T.P, Haringhata under Nadia Division, P.H.E. Dte. Kalyani Nadia. | Assistant Engineer | Junior Engineer 2 | ORD/000352/2023-2024 | 1029/KLYSD-I | 29/09/2023 | 29/11/2023 | M/S S.K. ENTERPRISE | 0.34 | 0.34 | 100 | 100
13 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR BARA ANDULIA MAHILA SAMITY NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  |  | BILL/00997/2023-2024 |  | 22/12/2023 | 22/12/2023 | BARA ANDULIA MAHILA SAMITY | 0.16 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  |  | BILL/00996/2023-2024 |  | 22/12/2023 | 22/12/2023 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.16 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  |  | BILL/01000/2023-2024 |  | 22/12/2023 | 22/12/2023 | BINAY BADAL DINESH CLUB | 0.16 | 0 | 0 | 0
16 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00088/2024-2025 | 46/PFMS | 14/05/2024 | 14/05/2024 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
17 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00129/2024-2025 | 72/PFMS | 13/06/2024 | 13/06/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
18 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00287/2024-2025 | 174/PFMS | 14/08/2024 | 14/08/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
19 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00579/2024-2025 | 348/PFMS | 26/11/2024 | 26/11/2024 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
20 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of Operational Charges of NGO managed Water Testing Laboratory at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. Financial Year: 2024-2025, Instalment: 1st |  |  | BILL/00307/2024-2025 | 185/PFMS | 21/08/2024 | 21/08/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.4 | 0 | 0 | 0
21 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00199/2024-2025 | 110/PFMS | 16/07/2024 | 16/07/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
22 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  |  | BILL/00998/2023-2024 |  | 22/12/2023 | 22/12/2023 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.16 | 0 | 0 | 0
23 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01236/2023-2024 | 519/PFMS | 09/02/2024 | 09/02/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
24 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01456/2023-2024 | 590/PFMS | 12/03/2024 | 12/03/2024 | BINAY BADAL DINESH CLUB | 0.61 | 0 | 0 | 0
25 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Operational charges of NGO Managed Laboratories (BINAY BADAL DINESH CLUB) at Nadia District. |  |  | BILL/00038/2024-2025 | 20/PFMS | 24/04/2024 | 24/04/2024 | BINAY BADAL DINESH CLUB | 0.35 | 0 | 0 | 0
26 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00084/2024-2025 | 49/PFMS | 14/05/2024 | 14/05/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
27 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00086/2024-2025 | 48/PFMS | 14/05/2024 | 14/05/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
28 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00130/2024-2025 | 73/PFMS | 13/06/2024 | 13/06/2024 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
29 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00410/2024-2025 | 238/PFMS | 10/09/2024 | 10/09/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
30 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00624/2024-2025 | 357/PFMS | 10/12/2024 | 10/12/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
31 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00625/2024-2025 | 354/PFMS | 10/12/2024 | 10/12/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
32 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | AD-HOC BONUS BILL FOR 01 NO BACTERIOLOGIST, 01 NO CHEMIST, 01 NO LAB ASSISTANT FOR W.B.C.A.D.C. RANAGHAT-II NGO LABORATORY PERSONNEL FOR THE YEAR 2022-2023 |  |  | BILL/00999/2023-2024 |  | 22/12/2023 | 22/12/2023 | W.B.C.A.D.C. RANAGHAT-II | 0.16 | 0 | 0 | 0
33 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA BARA ANDULIA MAHILA SAMITY NGO LAB FOR THE MONTH OF DEC-23. |  |  | BILL/01059/2023-2024 | 469/PFMS | 11/01/2024 | 11/01/2024 | BARA ANDULIA MAHILA SAMITY | 0.33 | 0 | 0 | 0
34 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01453/2023-2024 | 587/PFMS | 12/03/2024 | 12/03/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.61 | 0 | 0 | 0
35 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01452/2023-2024 | 586/PFMS | 12/03/2024 | 12/03/2024 | BARA ANDULIA MAHILA SAMITY | 0.61 | 0 | 0 | 0
36 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00003/2024-2025 | 02/PFMS | 10/04/2024 | 10/04/2024 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
37 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00582/2024-2025 | 351/PFMS | 26/11/2024 | 26/11/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
38 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00196/2024-2025 | 113/PFMS | 16/07/2024 | 16/07/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
39 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of Operational Charges of NGO managed Water Testing Laboratory at Haranagar SKUS LTD NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. 1st installment. |  |  | BILL/00308/2024-2025 | 186/PFMS | 21/08/2024 | 21/08/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.4 | 0 | 0 | 0
40 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00126/2024-2025 | 69/PFMS | 13/06/2024 | 13/06/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
41 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00626/2024-2025 | 355/PFMS | 10/12/2024 | 10/12/2024 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
42 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO LAB FOR THE MONTH OF DEC-23. |  |  | BILL/01057/2023-2024 | 467/PFMS | 11/01/2024 | 11/01/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.33 | 0 | 0 | 0
43 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED NGO LAB FOR THE MONTH OF DEC-23. |  |  | BILL/01058/2023-2024 | 468/PFMS | 11/01/2024 | 11/01/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.33 | 0 | 0 | 0
44 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | CHARGES FOR NGO LABORATORY MAINTAINING. |  |  | BILL/01293/2023-2024 |  | 15/02/2024 | 15/02/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.35 | 0 | 0 | 0
45 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Operational charges of NGO managed Laboratories (HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD.) at Nadia District. |  |  | BILL/00032/2024-2025 | 19/PFMS | 24/04/2024 | 24/04/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.35 | 0 | 0 | 0
46 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00002/2024-2025 | 01/PFMS | 10/04/2024 | 10/04/2024 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
47 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00006/2024-2025 | 05/PFMS | 10/04/2024 | 10/04/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
48 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00004/2024-2025 | 03/PFMS | 10/04/2024 | 10/04/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
49 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Arrangement for annual operational charges of Binoy Badal Dinesh Club NGO managed Water testing Laboratory under Nadia Division, PHE Dte. for 1st instalment of 2023-2024. |  |  | BILL/00151/2024-2025 | 96/PFMS | 03/07/2024 | 03/07/2024 | BINAY BADAL DINESH CLUB | 0.4 | 0 | 0 | 0
50 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00409/2024-2025 | 237/PFMS | 10/09/2024 | 10/09/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
51 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00197/2024-2025 | 111/PFMS | 16/07/2024 | 16/07/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
52 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR BINAY BADAL DINESH CLUB NGO LAB FOR THE MONTH OF DEC-23. |  |  | BILL/01060/2023-2024 | 470/PFMS | 11/01/2024 | 11/01/2024 | BINAY BADAL DINESH CLUB | 0.33 | 0 | 0 | 0
53 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01454/2023-2024 | 588/PFMS | 12/03/2024 | 12/03/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.61 | 0 | 0 | 0
54 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00405/2024-2025 | 234/PFMS | 10/09/2024 | 10/09/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
55 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00541/2024-2025 | 327/PFMS | 05/10/2024 | 05/10/2024 | BINAY BADAL DINESH CLUB | 0.63 | 0 | 0 | 0
56 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00127/2024-2025 | 70/PFMS | 13/06/2024 | 13/06/2024 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
57 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00283/2024-2025 | 171/PFMS | 14/08/2024 | 14/08/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
58 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00288/2024-2025 | 175/PFMS | 14/08/2024 | 14/08/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
59 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00408/2024-2025 | 236/PFMS | 10/09/2024 | 10/09/2024 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
60 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00286/2024-2025 | 173/PFMS | 14/08/2024 | 14/08/2024 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
61 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00623/2024-2025 | 358/PFMS | 10/12/2024 | 10/12/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
62 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00200/2024-2025 | 112/PFMS | 16/07/2024 | 16/07/2024 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
63 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01238/2023-2024 | 520/PFMS | 09/02/2024 | 09/02/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
64 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00627/2024-2025 | 356/PFMS | 10/12/2024 | 10/12/2024 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
65 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of Operational Charges of NGO managed Water Testing Laboratory at Binay Badal Dinesh Club NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. Financial Year: 2023-2024, Instalment: 2nd Period of Instalment month: 01-10-2023 to 31-03-2024 |  |  | BILL/00306/2024-2025 | 184/PFMS | 21/08/2024 | 21/08/2024 | BINAY BADAL DINESH CLUB | 0.35 | 0 | 0 | 0
66 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00406/2024-2025 | 235/PFMS | 10/09/2024 | 10/09/2024 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
67 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00581/2024-2025 | 347/PFMS | 26/11/2024 | 26/11/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
68 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00578/2024-2025 | 349/PFMS | 26/11/2024 | 26/11/2024 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
69 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00128/2024-2025 | 71/PFMS | 13/06/2024 | 13/06/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.45 | 0 | 0 | 0
70 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00540/2024-2025 | 326/PFMS | 05/10/2024 | 05/10/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.63 | 0 | 0 | 0
71 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01230/2023-2024 | 522/PFMS | 09/02/2024 | 09/02/2024 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
72 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01235/2023-2024 | 521/PFMS | 09/02/2024 | 09/02/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
73 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00085/2024-2025 | 47/PFMS | 14/05/2024 | 14/05/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
74 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00087/2024-2025 | 45/PFMS | 14/05/2024 | 14/05/2024 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
75 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at West Bengal Comprehensive Area Development Corporation NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00544/2024-2025 | 330/PFMS | 05/10/2024 | 05/10/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.63 | 0 | 0 | 0
76 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00198/2024-2025 | 109/PFMS | 16/07/2024 | 16/07/2024 | BARA ANDULIA MAHILA SAMITY | 0.45 | 0 | 0 | 0
77 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | MONTHLY REMUNERATION OF OF 01 NO CHEMIST, 01 NO BACTERIOLOGIST AND 01 NO LAB ASSISTANT FOR W.B.C.A.D.C. RANAGHAT-II NGO LAB FOR THE MONTH OF DEC-23. |  |  | BILL/01056/2023-2024 | 466/PFMS | 11/01/2024 | 11/01/2024 | W.B.C.A.D.C. RANAGHAT-II | 0.33 | 0 | 0 | 0
78 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01233/2023-2024 | 523/PFMS | 09/02/2024 | 09/02/2024 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
79 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/01455/2023-2024 | 589/PFMS | 12/03/2024 | 12/03/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.61 | 0 | 0 | 0
80 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00005/2024-2025 | 04/PFMS | 10/04/2024 | 10/04/2024 | HARANAGAR SAMABAY KRISHI UNNAYAN SAMITY LTD. | 0.45 | 0 | 0 | 0
81 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00542/2024-2025 | 329/PFMS | 05/10/2024 | 05/10/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.63 | 0 | 0 | 0
82 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Binoy Badal Dinesh Club NGO Managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00285/2024-2025 | 172/PFMS | 14/08/2024 | 14/08/2024 | BINAY BADAL DINESH CLUB | 0.45 | 0 | 0 | 0
83 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Nadia Zilla Ganatantric Mohila Samabay Rindan Samity Limited NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00580/2024-2025 | 350/PFMS | 26/11/2024 | 26/11/2024 | NADIA ZILLA GANATANTRIC MOHILA SAMABAY RINDAN SAMITY LIMITED | 0.45 | 0 | 0 | 0
84 | NADIA |  | Nadia Division | Operational charges of PHED & NGO Managed Drinking Water Testing Laboratories under Nadia Division, PHE Dte, related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission | SM/19066 | Support-WQMSP | Payment of remuneration for engagement of NGO Lab personnel (NGO Lab Chemist, NGO Lab Bacteriologist, NGO Lab Lab-Assistant) at Bara Andulia Mahila Samity NGO managed Water Testing Laboratory under Nadia Division, PHE Dte. |  |  | BILL/00543/2024-2025 | 328/PFMS | 05/10/2024 | 05/10/2024 | BARA ANDULIA MAHILA SAMITY | 0.63 | 0 | 0 | 0
Total | [13 empty] | 86.9 | 44.95 | 51.72