## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Fatepur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/07896 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Fatepur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl No.- 03) | Assistant Engineer-I | Junior Engineer-II | ORD/000185/2020-2021 | 159/NAD-I | 25/01/2021 | 26/03/2021 | TARUN KUMAR BHATTACHARYA | 96.53 | 189.63 | 196.43 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-I, (Fatepur), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/07896 | Retrofitting | Reconnection of Functional household tap connection including additional restoration and renovation work of pump house, boundary wall and path way at Zone-I,Fatepur under Surface based Water Supply PWSS of Haringhata & Chakdah (Part) under Haringhata Block under Nadia Arsenic Division-I,P.H.E Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000288/2023-2024 | 31/AE-I/NAD-I | 19/01/2024 | 18/02/2024 | SHYAMAL SHIL | 3.2 | 3.12 | 97.71 | 100
Total | [13 empty] | 99.73 | 192.75 | 193.27