## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/07899 | Retrofitting | Laying work of Upvc pipeline at Hapania,Singa, Thansara and other Mouzas under Nagarukhra -II G.P. under Zone-II (Hapania) under Surface Based Haringhata & Chakdah (Part) W/S Scheme under Haringhata Block in the district of Nadia under Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I,Junior Engineer-II | ORD/000078/2022-2023 | 88 /AE-I/NAD-I | 28/04/2022 | 13/05/2022 | TARUN KUMAR BHATTACHARYA | 4.84 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/07899 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. 06) | Assistant Engineer-I | Junior Engineer-II | ORD/000205/2020-2021 | 154/NAD-I | 25/01/2021 | 26/03/2021 | SATYABRATA CHAKRABORTY | 95.8 | 95.63 | 99.82 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-II, (Hapania), Part-I at Haringhata Block by retrofitting of Surface Water based PWSS for Haringhata & Chakdah (Part) Water Supply Scheme | SM/07899 | Retrofitting | Inter-Connection with M.S Pipeline to Distribution Pipeline of Surface Water Based Piped Water Supply Scheme for arsenic affected areas of Haringhata & Chakdah (Part) (Hapania Zone-II) under Haringhata Block under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. Tender No.-04/NAD-I/2021-2022. | Assistant Engineer-I | Junior Engineer-II | ORD/000041/2021-2022 | 87/AE-I/NAD-I | 05/05/2021 | 04/06/2021 | SATYABRATA CHAKRABORTY | 4.17 | 4.17 | 99.99 | 0
Total | [13 empty] | 104.82 | 99.8 | 95.22