## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-VIII, (BARBERIA), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/07900 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara/Jalswapna for Zone-VIII, (Barberia), Part-I at Chakdah Block by retrofitting of Surface Water Based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer-I | Junior Engineer-I | ORD/000207/2020-2021 | 312/NAD-I | 08/02/2021 | 09/05/2021 | MONDAL PRECESION PVT. LTD. | 95.18 | 125.29 | 131.64 | 100
Total | [13 empty] | 95.18 | 125.29 | 131.64