## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (PURBA BISHNUPUR), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/07903 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Dhara/Jal Swapna for Zone-V, (Purba Bishnupur) Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, P.H.E. Dte (Sl. NO. 04) Tender No. 218/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | ORD/000170/2020-2021 | 311/NAD-I | 08/02/2021 | 09/05/2021 | MAHAVIR PUMPS MANUFACTURING PRIVATE LIMITED | 97.1 | 165.71 | 170.66 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-V, (PURBA BISHNUPUR), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/07903 | Retrofitting | Retrofitting work for Purba Bishnupur Zone -V of Surface Water Based PWSS for Chakdah Part Water Supply Scheme under Office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte.( Sl.no. 06) | Assistant Engineer-I | Junior Engineer-I | ORD/000283/2022-2023 | 1473/NAD-I | 22/08/2022 | 21/10/2022 | APURBA MANDAL | 1.77 | 1.55 | 87.75 | 0
Total | [13 empty] | 98.87 | 167.27 | 169.18