## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Simurali), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/07999 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, Shimurali, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000022/2021-2022 | 865/NAD-I | 15/06/2021 | 14/08/2021 | ALOK ENTERPRISE | 80.87 | 80.7 | 99.78 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-X, (Simurali), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/07999 | Retrofitting | Hiring of 1 (One) no Diesel Luxury Taxi/Maxi Cab/Motor Cab on Daily basis for monitoring of JJM works and progress of JJM works (Such as identification of land etc) under the office of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000182/2023-2024 | 383/AE-I/NAD-I | 01/09/2023 | 01/03/2024 | ANURADHA DHARA | 2.4 | 1.66 | 69.3 | 20
Total | [13 empty] | 83.27 | 82.36 | 98.91