## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/08003 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000009/2021-2022 | 773/NAD-I | 04/05/2021 | 03/07/2021 | H I ENTERPRISE | 95.74 | 40.97 | 42.8 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/08003 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Bhayna Zone-II Part-I at Hanskhali Block by retrofitting of Ground Water based PWSS for Bhayna Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. NO. -01) Tender no.- 230/NAD-I/2020-2021. | Assistant Engineer-II | Junior Engineer-IV | ORD/000192/2020-2021 | 290/NAD-I | 04/02/2021 | 21/03/2021 | CHANDAN ROY | 43.9 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/08003 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Ukilnara Zone - II at Ranaghat - I Block by retrofitting of Ground Water based PWSS for Ukilnara - Zone - II Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte.(Sl. No.-08) Tender No. 234/NAD-I/2020-2021. | Assistant Engineer-I | Junior Engineer-I | ORD/000189/2020-2021 | 292/NAD-I | 04/02/2021 | 21/03/2021 | M/S UMA CONSTRUCTION | 43.74 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/08003 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, Masra, Part-I, Ukhilnara -II, at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000391/2020-2021 | 292 / NAD-I | 04/02/2021 | 21/03/2021 | M/S UMA CONSTRUCTION | 43.74 | 0 | 0 | 60
5 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-III, (Masra), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/08003 | Retrofitting | Supply of 1(one )no. Motor Cab ( Luxury Taxi) on hire basis for official use of the Executive Engineer , Nadia Arsenic Division -I, P.H.E.Dte. for the period from ( 15.07.22 to 14.07.23i.e. for 1(one) year .(sl.01) | Assistant Engineer-I | Junior Engineer-IV | ORD/000304/2021-2022 | 173 / AE-I/NAD-I | 14/07/2021 | 14/07/2022 | AVINABA ENGINEERING CONCERN | 5.34 | 0 | 0 | 100
Total | [13 empty] | 232.46 | 40.97 | 17.63