## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Zone-IX, (Ghetugachhi), Part-I at Chakdaha Block by retrofitting of Surface Water based PWSS for Chakdah (Part) Water Supply Scheme | SM/08006 | Retrofitting | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Zone IX Ghetugachi Part-I at Chakdah Block by retrofitting of Surface Water based PWSS for Chakdah Part Water Supply Scheme under Nadia Arsenic Division I PHE Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000019/2021-2022 | 784/NAD-I | 05/05/2021 | 04/07/2021 | GHOSH ENTERPRISE | 92.92 | 81.07 | 87.25 | 100
Total | [13 empty] | 92.92 | 81.07 | 87.25