## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Muragachha Zone-I Part-II, at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme | SM/08012 | Retrofitting | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Muragachha Zone I Part II at Hanskhali Block by retrofitting of Ground Water based PWSS for Muragachha Water Supply Scheme under Nadia Arsenic Division I PHE Dte. | Assistant Engineer-II | Junior Engineer-IV | ORD/000016/2021-2022 | 781/NAD-I | 05/05/2021 | 04/07/2021 | MONDAL ENTERPRISE | 89.68 | 133.41 | 148.76 | 100
Total | [13 empty] | 89.68 | 133.41 | 148.76