## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Gayeshpur Zone-I, at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme | SM/08014 | Retrofitting | Providing FHTC Functional Household Tap Connection under Jaldhara Jal Swapna for Gayeshpur Zone I at Santipur Block by retrofitting of Ground Water based PWSS for Gayeshpur Water Supply Scheme under Nadia Arsenic Division I PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000017/2021-2022 | 782/NAD-I | 05/05/2021 | 04/07/2021 | APURBA MANDAL | 96.99 | 90.79 | 93.6 | 100
Total | [13 empty] | 96.99 | 90.79 | 93.6