## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar Part-II, at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme | SM/08018 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Birnagar, Part-II at Ranaghat-I Block by retrofitting of Ground Water based PWSS for Birnagar Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000002/2021-2022 | 766/NAD-I | 04/05/2021 | 03/07/2021 | CALCON CONSTRUCTION | 63.98 | 78.39 | 122.53 | 100
Total | [13 empty] | 63.98 | 78.39 | 122.53