## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia Part-II, at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme | SM/08019 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia, Part-II at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-II | ORD/000012/2021-2022 | 777/NAD-I | 05/05/2021 | 04/07/2021 | J.D.J. ENTERPRISE | 97.11 | 0 | 0 | 50
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia Part-II, at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme | SM/08019 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission (JJM) for Mouza-Beharia at Santipur Block by augmentation of Ground Water Based PWSS for Beharia W/S Scheme under Nadia Arsenic Division-I, PHE Dte (SL.NO.03) | Assistant Engineer-I | Junior Engineer-I | ORD/000148/2022-2023 | 3326 / NAD-I | 16/12/2022 | 30/01/2023 | CHOWDHURY & CO. | 67.83 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Beharia Part-II, at Santipur Block by retrofitting of Ground Water based PWSS for Beharia Water Supply Scheme | SM/08019 | Retrofitting | Pipeline connection with manifold to dedicated line under Jal Jeevan Mission (JJM) at Shantipur Block by retrofitting o Ground Water based PWSS for Beharia Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. (Sl. No. ¿ 01) | Assistant Engineer-I | Junior Engineer-II | ORD/000290/2023-2024 | 28/AE-I/NAD-I | 19/01/2024 | 03/02/2024 | DEBASHISH DEY | 0.96 | 0 | 0 | 100
Total | [13 empty] | 165.9 | 0 | 0