## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-II Part-II, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme | SM/08020 | Retrofitting | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur-Krishnapur, Zone-II, Part-II at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur-Krishnapur Water Supply Scheme under Nadia Arsenic Division-I, PHE Dte. | Assistant Engineer-II | Junior Engineer-III | ORD/000004/2021-2022 | 768/NAD-I | 04/05/2021 | 03/07/2021 | MALI CONSTRUCTION | 34.25 | 33.8 | 98.69 | 100
2 | NADIA |  | Nadia Arsenic Division I | Providing FHTC (Functional Household Tap Connection) under Jaldhara / Jal Swapna for Halalpur Krishnapur Zone-II Part-II, at Ranaghat-II Block by retrofitting of Ground Water based PWSS for Halalpur Krishnapur Water Supply Scheme | SM/08020 | Retrofitting | Supply of 1(one) no. Motor Cab (Luxury Taxi) on hire basis of mass emission standard like Bharat Stage - III and Higher and purchased on or after 01.05.2008 with diesel / LPG / CNG Engine, non-air-conditioned for official use of the Executive Engineer, Nadia Arsenic Division-I, P.H.E. Dte. [For the period of 6 (six) Months] | Assistant Engineer-I | Junior Engineer-III | ORD/000062/2023-2024 | 0262/AE-I/NAD-I | 31/05/2023 | 30/11/2023 | MUKHERJEE CONSTRUCTION | 0.88 | 0 | 0 | 100
Total | [13 empty] | 35.14 | 33.8 | 96.21